## Sheet1
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
Task/Activity | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
General Tasks
Cross-WG Collaboration (T13) | Year 1 Q2: x; Year 1 Q3: D17; Year 2 Q2: x; Year 2 Q4: D14; Year 3 Q2: x; Year 3 Q3: D17; Year 4 Q2: x; Year 4 Q3: D14
Dissemination, Impact (T14) | Year 1 Q3: D13; Year 1 Q4: x; Year 2 Q3: D15; Year 2 Q4: x; Year 3 Q3: x; Year 3 Q4: x; Year 4 Q2: D15; Year 4 Q3: x; Year 4 Q4: x
Ethical Compliance (T15) | bar: Year 1 Q4; Year 2 Q4; Year 3 Q4; Year 4 Q4
Communication Plan (T16) | bar: Year 1 Q4; Year 2 Q4; Year 3 Q4; Year 4 Q4
Quarterly CG Meetings (T17) | bar: Year 1 Q1 to Year 4 Q4
Annual MC Meetings (T18) | Year 1 Q3: x; Year 1 Q4: D18; Year 2 Q3: x; Year 3 Q3: x; Year 3 Q4: D18; Year 4 Q3: x
Activities
STSMs | Year 1 Q3: x; Year 2 Q3: x; Year 2 Q4: D14; Year 3 Q3: x; Year 4 Q2: D14; Year 4 Q3: x
VMGs | Year 1 Q4: x; Year 2 Q1: D14; Year 2 Q4: x; Year 3 Q4: x; Year 4 Q1: D14; Year 4 Q4: x
WG Meetings |  | x |  | x |  | x | D19 | x |  | x | D19 | x |  | x |  | x
Action Conferences | Year 2 Q1: x; Year 2 Q2: D14; Year 3 Q1: x; Year 3 Q2: D18; Year 4 Q1: x; Year 4 Q2: D14
PhD Training Schools | Year 1 Q3: x; Year 1 Q4: D16; Year 2 Q3: x; Year 2 Q4: D14; Year 3 Q3: x; Year 3 Q4: D14; Year 4 Q1: D16; Year 4 Q3: x
Special Isssue | Year 1 Q4: D15; Year 2 Q4: x; Year 3 Q4: D15; Year 4 Q4: x
WG1: Data-driven processes
Data Privacy Guidelines (T1) | bar: Year 1 Q1 to Year 2 Q1; Year 4 Q3
Fairness Models (T2) | bar: Year 2 Q1 to Year 3 Q1; Year 4 Q3
Federated Learning (T3) | bar: Year 3 Q1 to Year 4 Q1; Year 4 Q3
WG2: Generative AI
Portfolio Models (T4) | bar: Year 1 Q1 to Year 2 Q1; Year 4 Q3
Risk Management Models (T5) | bar: Year 2 Q1 to Year 3 Q1; Year 4 Q3
Personalized Models (T6) | bar: Year 3 Q1 to Year 4 Q1; Year 4 Q3
WG3: XAI and Bias
XAI Methods (T7) | bar: Year 1 Q3; Year 2 Q1 to Year 3 Q1
Transparent Networks (T8) | bar: Year 1 Q3; Year 3 Q1 to Year 4 Q1
Bias Mitigation (T9) | bar: Year 1 Q3; Year 3 Q4 to Year 4 Q4
WG4: Sustainable Finance
ESG Sentiment Analysis (T10) | Year 1 Q3: x; Year 2 Q1: x; Year 2 Q2: x; Year 2 Q3: x; Year 2 Q4: x; Year 3 Q1: D10
News Analysis (T11) | Year 1 Q3: x; Year 3 Q1: x; Year 3 Q2: x; Year 3 Q3: x; Year 3 Q4: x; Year 4 Q1: D11
ESG Scoring Models (T12) | Year 1 Q3: x; Year 3 Q4: x; Year 4 Q1: x; Year 4 Q2: x; Year 4 Q3: x; Year 4 Q4: D12
D1: Data Privacy Guidelines for Financial Applications: A comprehensive report outlining best practices for data privacy in financial applications. D2: Fairness Models for Financial Algorithms: Models and metrics to ensure fairness in algorithms. D3: Federated Learning Implementation: A report on the techniques and protocols for implementing federated learning in financial applications. D4: Advanced Portfolio Optimization Models: A document detailing advanced portfolio optimization techniques using Transformer Neural Networks. D5: Enhanced Risk Assessment Models: Models and algorithms that leverage generative AI for real-time financial risk assessment. D6: Personalized Financial Advice Models: Models that provide tailored financial advice. D7: Scalable XAI Methods: A report on scalable XAI methods tailored for financial time-series data. D8: Transparent Transformer Neural Networks: Documentation and code for transparent and interpretable Transformer Neural Network architectures. D9: Algorithmic Bias Mitigation Strategies: A report outlining strategies for measuring and mitigating algorithmic bias in financial applications. | Year 2 Q1: D10: ESG Sentiment Analysis: Models and findings on sentiment analysis related to Environmental, Social, and Governance factors. D11: News and Reports Analysis: Algorithms for analyzing news to extract ESG-related information. D12: Real-Time ESG Scoring Models: A real-time scoring system for assessing the ESG performance. D13: Online Presence and Social Media: A website and LinkedIn, Facebook and Twitter accounts. D14: Data Collection: 20 datasets to be used for research, publicly accessible. D15: Publication Plan: A green open-access repository featuring 80 papers, and 4 special issues. D16: Training Materials: Slides and video material from at least two PhD training schools per year. D17: Research Proposals: Submission of at least 40 research proposals, both national and European. D18: Award: An award for the best Young Researcher presentation at the annual MC meeting. D19: Gender Balance Reports: Periodic reports tracking gender balance and other inclusivity metrics.