Work And Budget Plan

CA19130 Grant Agreement Period 4

01/11/2022 to 31/10/2023

Action Profile

Action General Information

Action Code CA19130 MC Chair Prof Jörg Osterrieder

Action Title CA19130 - Fintech and Artificial Intelligence in Finance - Towards a transparent financial industry

MOU 033/20 Draft MOU OC-2019-1-24059 CSO Approval Date 2020-03-31

Action Start Date 14/09/2020 Action End Date 13/09/2024 Science Officer Dr Ralph Stuebner Administrative Officer Ms Rose Cruz Santos

Participation in the Action:

Number of COST Full or Cooperating

Members

COST

Partner

Members

Countries

Specific

Organisations

Near

Neighbour Countries

Third States

Total

COST Members / Specific Organisations represented in the MC

Countries represented in the Working Groups

Nominated MC Members / MC Observers

Approved Working Group members

Submitted : 2023-03-31 6:34 PM Generated : 2023-04-05 9:47 AM

38 0 0 n.a. n.a. 38 ITC 58%

Non-ITC 42%

40 0 0 3 7 50 ITC 58%

Non-ITC 43%

Individuals

71 0 0 n.a. n.a. 71 ITC 56%

Non-ITC 44%

253 0 0 7 9 272 ITC 59%

Non-ITC 41%

Working Groups

WG Title WG Leader Number of WG members

WG1 Transparency in FinTech Prof Wolfgang Härdle 169

WG2 Transparent versus Black Box Decision Support Models in the Financial Industry

WG3 Transparency into Investment Product Performance for Clients

Dr Petre Lameski 179 Prof Peter Schwendner 130

2

MoU objectives, Action deliverables and Grant Agreement Period Goals Action Objectives from MoU

Aim/primary Objective

establish a large and interconnected community across academia, public institutions and industry focusing on Financial Technology and Artificial Intelligence, improving transparency in financial services, especially in and through FinTech, in financial modelling and investment performance evaluation

Secondary objectives

1. To develop blended approaches to evaluate innovative financial services and their providers, especially in the FinTech domain, building on Machine Learning methods, focussing on prediction (early warning) of operational fragility, fraudulent and illegal behaviour ranging from appropriation of loaned funds to money-laundering activities.

2. The development of conceptual and methodological tools for establishing when black-box models are admissible and, to the extent possible, making them more transparent and/or replacing them with interpretable and explainable models.

3. To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications.

4. Pruning and improvement of the vast array of performance attribution models by contributing to the development of methodologies for reducing the false discovery rate in financial research and applied financial investment management.

5. Disseminate to the public and share with regulators the results on investment product performance evaluation.

6. Creation of the first European platform comparing the out-of-sample performance of banks' investment products, insurance-linked investment products and asset management products available to the general public.

7. Create an excellent network of researchers in Europe with lasting collaboration beyond the lifetime of the Action.

8. Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

9. Bridging the gap between practitioners from the finance industry, academics and regulators by setting up a common knowledge exchange platform.

10. Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

11. Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility.

12. Overcome the siloing of research topics by country and achieve geographical and demographical diversity, with special attention to COST Inclusiveness Target countries.

13. Prepare competitive European researchers for a fruitful career in an international environment through intensive use of Short Term Scientific Missions (STSM) and joint educational programs with industrial partners.

14. Maximize the job opportunities for PhD students and Early Career Investigators. 15. Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public.

16. Significantly improve the gender equality in the fields of the Action.

3

Action Deliverables Deliverable Month 1. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36) 6

2. Report on good examples and best practices for a transparent finance industry with guidelines

12

to improve transparency

3. A database which contains pre-ICO documentation and post-ICO performance (ROI and

24

lifespan)

4. A database which contains data on crowdfunding/P2P platform features useful for rating

24

platform integrity and to predict fraud

5. A discussion paper for possible approaches to building a statistically valid back-testing

24

framework

6. An internal database of collected (scraped) financial time series from exchanges and regional

24

consolidation platforms optimised for accessibility to all partners

7. Discussion papers (DP) on the methodology for evaluating/rating ICOs and crowdfunding/P2P

36

platforms and for detection/early warning about fraud/illegal behaviour with emphasis on the application of AI tools

8. Position papers, aimed at regulators and policy-makers, on methodology (with examples of

36

formal criteria) for testing AI techniques in real-time

9. Handbook and/or wiki page describing potential approaches to tackle risk management issues

36

related to blockchain assets and crowdfunding/P2P lending

10. A position paper and roadmap on mitigating risks connected with the increased use of digital

48

assets

11. Methodological discussion paper on the design of stress tests for the evaluation of AI and ML

48

models under shifting financial conditions to improve the robustness of models 12. Methodological discussion papers on AI models to generate “failed trials” of investment

48

product producers and on quantitative strategies with the usage of the promising field of network data analysis

13. Four annual reports (for lay audience) distributed via local and national media 48

14. Key software (codes, packages) developed by each of the Working Groups in line with their

48

objectives

15. An edited volume containing scientific achievements of the Action (dummy text to delete) 48 4

Grant Agreement Period

Grant Agreement Period Start Date

Grant Agreement Period Goals

01/11/2022 Grant Agreement Period End Date

31/10/2023

Number Grant Agreement Period Goal MoU Objective(s) it relates to

GAPG 1 Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions

Secondary objective 2 Secondary objective 10

GAPG 2 Paper on testing AI techniques Secondary objective 7 Secondary objective 8

GAPG 3 Presentations and dissemination of research results on backtesting investment strategies, performance explanation/attribution and synthetic data generation

GAPG 4 Publications on investment and hedging strategies on cryptos/digital assets and on traditional assets

accounting for ESG criteria

GAPG 5 Publications that tackle the issue of diversity in AI and Fintech

GAPG 6 Finishing ongoing publications (datathon, financial literacy and women in editorial board of financial

papers)

Secondary objective 2 Secondary objective 4 Secondary objective 5 Secondary objective 6 Secondary objective 15

Secondary objective 5 Secondary objective 15

Secondary objective 11 Secondary objective 15 Secondary objective 16

Secondary objective 11 Secondary objective 15 Secondary objective 16

GAPG 7 Involve associations with a diversity focus Secondary objective 9 Secondary objective 15

GAPG 8 Annual report on the COST Action Secondary objective 8 Secondary objective 9

Secondary objective 10

GAPG 9 Edited volume containing achievements Secondary objective 8 Secondary objective 9

Secondary objective 10

GAPG 10 Involve policy makers and disseminate results to them Secondary objective 5 Secondary objective 9

Secondary objective 15

GAPG 11 Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Secondary objective 16

5

Work and Budget Plan for the Grant Agreement Period Work and Budget Plan Summary

A. COST Networking Tools EUR (1) Meetings 117,889.40 (2) Training Schools 58,594.00 (3) Mobility of Researchers and Innovators 43,300.00 (4) Presentation at Conferences organised by Third Parties 2,000.00 (5) Dissemination and Communication Products 2,500.00 (6) Other Expenses Related to Scientific Activities (OERSA) 0.00 B. Total Science Expenditure (sum of (1) to (6)) 224,283.40

C. Financial and Scientific Administration and Coordination (FSAC) (max. of 15% of B)

33,642.51

Total Grant (B+C) 257,925.91 6

Meetings Overview

Meeting Title Meeting Type Dates Location ITC Total Cost (EUR)

Diversity

challenges and stakeholders' engagement

Core Group Meeting, Working Group Meeting

01/02/2023 - 02/02/2023

Cluj Napoca (Romania)

Yes 12,331.40

Diversity

challenges for a sustainable

Fintech

Core Group Meeting, Workshops/Conferences

13/04/2023 - 14/04/2023

Pavia (Italy) No 9,024.00

COST FinAI - Fintech and AI in Finance -

Policy

implications

COST FinAI

WG3:

Transparency of Digital Asset Investments

Women in

Fintech III -

Portugal

Workshops/Conferences 15/05/2023 - 16/05/2023

Working Group Meeting 26/05/2023 - 26/05/2023

Workshops/Conferences 01/06/2023 - 02/06/2023

Brussels

(Belgium)

Winterthur (Switzerland)

Lisbon

(Portugal)

No 15,148.00 No 5,322.00 Yes 11,835.00

COST FinAI

meets Romania

Machine

Learning,

Artificial

Intelligence and Data Protection in Fintech

Conference

WG1, WG2, CG

Core Group Meeting, Working Group Meeting

Core Group Meeting, Working Group Meeting

16/06/2023 - 16/06/2023

06/07/2023 - 07/07/2023

N/A N/A 500.00 Dublin (Ireland) No 9,424.00

Nordic AI and Fintech

COST FinAI - Fintech and AI in Finance - MC, WG and Core group meeting

Details

Core Group Meeting, Working Group Meeting

Core Group Meeting, Management Committee Meeting, Working Group Meeting

10/07/2023 - 11/07/2023

27/09/2023 - 28/09/2023

Helsinki

(Finland)

Bern

(Switzerland)

No 13,252.00 No 41,053.00

Total 117,889.40

Title of the Meeting Diversity challenges and stakeholders' engagement Meeting Type(s) Core Group Meeting,Working Group Meeting

Grant Period Goal(s) it will address

Presentations and dissemination of research results on backtesting investment strategies, performance explanation/attribution and synthetic data generation,Finishing ongoing publications (datathon, financial literacy and women in editorial board of financial papers),Annual report on the COST Action,Edited volume containing achievements

7

Description As this will be the first in person meeting of the Action in 2023, during the Core Group meeting (approx. 2 hours) the status of the Action will be assessed,

especially in terms of the objectives and deliverables - what was achieved in GP2

and what is running or has to be achieved in GP3. The Diversity Team will meet

after, to assess the diversity report for GP2 and prepare the strategy for GP3,

especially to prepare the Women in Fintech III Conference in May 2023, in

Coimbra, Portugal. Additionally, a special paper session will be dedicated to

presentation of research conducted by the diversity team. WG1 and WG2 will meet

in parallel on the 2nd day, to discuss research conducted in each of them, on one

hand, and their strategies related to objectives and deliverables, on the other. This

meeting is also related to the Action’s Strategy to engage stakeholders - related to

this, the status of the strategy’s fulfilment will be assessed and actions to enhance

cooperation with the stakeholders will be discussed. For this, the meeting will end

with a round table with the representatives of the Romanian FinTech sector and

the IT companies working in the field. One of the meeting’s goals is to build the

action plan for the construction of the first FinTech report for the Balkans, once

again related to the Action’s strategy to engage stakeholders. Additionally, a

special session dedicated to PhD students and young researchers will be

organized. https://www.meetup.com/fintech_ai_in_finance/events/289867639/?

isFirstPublish=true Support, taking COST FinAI contributions into account, will be

prioritised: 1) young researchers from ITC 2) ITC 3) young researchers non-ITC.

Senior researchers from non-ITC are expected to use their own travel funds.

Output(s) Abstracts of presentations will be made available online (upon permission by authors). Strategies of the Action for GP3 will be monitored in terms of

implementation and reporting, along with starting constructing the strategies for

GP4. More specifically, participants will work on the diversity strategy, the

stakeholders one and the WG1 and WG2 ones. The event will also allow

interaction among its members. Societal implications in the Fintech sector with

research proposals. Deliverable 8 will be finished. Report on good examples and

best practices for a transparent finance industry with guidelines to improve

transparency

Location Cluj Napoca (Romania) ITC Yes

Start Date 2023-02-01 09:00:00 End Date 2023-02-02 17:00:00

Duration 2 days Attendance Type Hybrid

Total number of expected participants

40 Number of participants expected to be

15

reimbursed from COST funds

Daily allowance (EUR) 187.00 Average number of daily allowances per

0

participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

688.76

688.76

10,331.40

40 Local Organiser Support (EUR) 2,000.00 12,331.40

Title of the Meeting Diversity challenges for a sustainable Fintech

Meeting Type(s) Core Group Meeting,Workshops/Conferences

8

Grant Period Goal(s) it will address

Publications that tackle the issue of diversity in AI and Fintech,Finishing ongoing publications (datathon, financial literacy and women in editorial board of financial papers),Involve associations with a diversity focus,Annual report on the COST Action,Edited volume containing achievements,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description https://www.meetup.com/fintech_ai_in_finance/events/288557097/ Core group meeting to discuss the current status of MoU and GP3 achievements. The event

will be hybrid to ensure maximum participation Diversity meeting to discuss

diversity goals and achievements and discuss potential adjustments. The diversity

meeting will focus on these topics • Women in fintech III conference • ongoing

projects and initiatives by diversity team members (e.g. VMG awarded to diversity

team members, research projects run by members, etc.) • any other issues 2nd

COST FinAI workshop on Environmental finance for the common good - Fintech

and AI for more sustainable societies: event dedicated to opportunities and

obstacles to more inclusive and sustainable societies prompted by Fintech and AI

tools applied to finance and investment evaluation in a multidisciplinary setting.

Workshop with COST FinAI organizers and speakers (more than 70%) One

session dedicated to PhD students and ECI. Each presenter will be assigned a

discussant to get feedback. The activity hence aims at bringing together

academics, early career investigators, phd students, the industry and policy

makers to discuss around the issue of sustainability and if and how Fintech

applications pose an opportunity or a threat to a more sustainable and more

inclusive society. New methodologies that employ artificial intelligence in this area

will also be presented and discussed. Support, taking COST FinAI contributions

into account, will be prioritised: 1) young researchers from ITC 2) ITC 3) young

researchers non-ITC. Senior researchers from non-ITC are expected to use their

own travel funds.

Output(s) Abstracts of papers presented will be made available online on the website of the event (upon permission by authors) A selection of papers presented during the

conference, relevant to the COST FinAI topics, will be invited for submission in

open access journals. The event will allow interaction among its members during

breaks and social events organised; discuss state of the art and future planning to

successfully reach CA19130 objectives; Planning of future events by cost diversity

team to reach CA19130 objectives in terms of diversity. Deliverable 2. will be

done. A database which contains data on crowdfunding/P2P platform features

useful for rating platform integrity and to predict fraud

Location Pavia (Italy) ITC No

Start Date 2023-04-13 13:00:00 End Date 2023-04-14 16:00:00

Duration 2 days Attendance Type Hybrid

Total number of expected participants

40 Number of participants expected to be

8

reimbursed from COST funds

Daily allowance (EUR) 201.00 Average number of daily allowances per

3

participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

400.00

1,003.00

8,024.00

40 Local Organiser Support (EUR) 1,000.00 9,024.00

9

Title of the Meeting COST FinAI - Fintech and AI in Finance - Policy implications Meeting Type(s) Workshops/Conferences

Grant Period Goal(s) it will address

Involve policy makers and disseminate results to them,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description The Workshop (two full days) shall highlight the findings of the Action as it relates to policy implications. Representatives from the WG will present their findings and

put them into context of policy implications. Policy makers from the EU will be

invited to attend and show their point of view and to discuss with Action

participants. Support, taking COST FinAI contributions into account, will be

prioritised: 1) young researchers from ITC 2) ITC 3) young researchers non-ITC.

Senior researchers from non-ITC are expected to use their own travel funds.

Output(s) Dissemination of the COST Action results to policy makers, white paper on policy implications of our Action. Receiving input from policykmakers. Deliverable 4 will

be done. A position paper and roadmap on mitigating risks connected with the

increased use of digital assets Obj 3. To receive input from regulators and

practitioners' communities and to validate results with regard to increasing

transparency of artificial intelligence applications will be tackled.

Location Brussels (Belgium) ITC No Start Date 2023-05-15 09:00:00 End Date 2023-05-16 17:00:00 Duration 2 days Attendance Type Hybrid

Total number of expected participants

50 Number of participants

14

expected to be

reimbursed from COST

funds

Daily allowance (EUR) 220.00 Average number of daily

3

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

422.00

1,082.00

15,148.00

40 Local Organiser Support (EUR)

15,148.00

0.00

Title of the Meeting COST FinAI WG3: Transparency of Digital Asset Investments Meeting Type(s) Working Group Meeting

Grant Period Goal(s) it will address

Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions

10

Description Working Group 3 of the COST Action CA 19130 Fintech and Artificial Intelligence in Finance will organise an interdisciplinary meeting open to all working groups of

the Action. In line with the item “Capacity Building 2”, we intend to bring together

experts from technological, quantitative, and economic fields in order to discuss

research questions relating to digital assets and investing that can best be

addressed in an interdisciplinary setting. Moreover, there will be ample time for

open discussions regarding past accomplishments and current deliverables of the

Action, as well as future joint research projects. In particular, we will address

Deliverables 4 and 10 of the Action. Support, taking COST FinAI contributions into

account, will be prioritised: 1) young researchers from ITC 2) ITC 3) young

researchers non-ITC. Senior researchers from non-ITC are expected to use their

own travel funds.

Output(s) The working group meeting will facilitate the establishment of joint research projects with publications as outputs. The face-to-face working group meeting will

strengthen the cooperation among researchers and across working groups.

Location Winterthur (Switzerland) ITC No Start Date 2023-05-26 09:00:00 End Date 2023-05-26 17:00:00 Duration 1 day Attendance Type Hybrid

Total number of expected participants

40 Number of participants

6

expected to be

reimbursed from COST

funds

Daily allowance (EUR) 209.00 Average number of daily

2

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

469.00

887.00

5,322.00

20 Local Organiser Support (EUR)

5,322.00

0.00

Title of the Meeting Women in Fintech III - Portugal Meeting Type(s) Workshops/Conferences

Grant Period Goal(s) it will address

Publications that tackle the issue of diversity in AI and Fintech,Finishing ongoing publications (datathon, financial literacy and women in editorial board of financial papers),Involve associations with a diversity focus

Description The event is titled Women in Fintech and AI and it is the third edition of the annual event organised by the diversity team of CA19130. The event aims at bringing

together academia, industry and policy maker to discuss gender equality and how

AI and Fintech pose opportunities and challenges to a more inclusive society.

https://www.meetup.com/en-US/fintech_ai_in_finance/events/288557097/ I added:

Support, taking COST FinAI contributions into account, will be prioritised: 1) young

researchers from ITC 2) ITC 3) young researchers non-ITC. Senior researchers

from non-ITC are expected to use their own travel funds.

11

Output(s) Greater awareness of the role of Women in the financial industry and in the technological development Deliverable 15 will be done. Strategy to engage

stakeholders in the Action (including revisions in month 24 and 36) by including

policy makers, associations, and the industry, and Obj 3.To receive input from

regulators and practitioners' communities and to validate results with regard to

increasing transparency of artificial intelligence applications. And Obj 9- Bridging

the gap between practitioners from the finance industry, academics and regulators

by setting up a common knowledge exchange platform. And Obj 15 Disseminate

the results of the Action's activities to the scientific community, European

institutions and to the general public.

Location Lisbon (Portugal) ITC Yes Start Date 2023-06-01 09:00:00 End Date 2023-06-02 17:00:00 Duration 2 days Attendance Type Hybrid

Total number of expected participants

40 Number of participants

11

expected to be

reimbursed from COST

funds

Daily allowance (EUR) 195.00 Average number of daily

3

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

400.00

985.00

10,835.00

40 Local Organiser Support (EUR)

11,835.00

1,000.00

Title of the Meeting COST FinAI meets Romania Meeting Type(s) Core Group Meeting,Working Group Meeting

Grant Period Goal(s) it will address

Presentations and dissemination of research results on backtesting investment strategies, performance explanation/attribution and synthetic data generation,Involve policy makers and disseminate results to them,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description 1 plenary sessions of the Core group – 2h · 1 plenary session for WG1 – 2h · 1 plenary session for WG2 – 2h · 1 plenary session for WG3 – 2h · 1 plenary

session – meeting with the Romanian FinTech Sector – 2h . Participation to

sessions of ICESS 2022 possible for free (if schedule permits) The main goal of

the 1-day event is to facilitate the meeting of: 1. The core group members to

discuss the status of the Action, the status of the deliverables and construction of

GP3 report. 2. WGs meetings to evaluate the achievements of the group, build the

WG’s reports and strategy for GP4, presentation of the research conducted by the

group members in order to enhance cooperation. 3. Meeting the Romanian

FinTech representatives and the local IT companies working in the field in order to

enhance the cooperation with the stakeholders. 4. Attend the sessions of ICESS

2022 in order to increase the visibility of the network and attract new members for

GP4 (if it fits to the schedule) The link is: https://icess.ase.ro/5th-icess/program/

COST events will be scheduled entirely outside relevant sessions for our network.

ICESS stands for 5th International Conference on Economics and Social

Sciences. Support, taking COST FinAI contributions into account, will be

prioritised: 1) young researchers from ITC 2) ITC 3) young researchers non-ITC.

Senior researchers from non-ITC are expected to use their own travel funds.

12

Output(s) Abstracts of presentations will be made available online (upon permission by authors) Implication in the Fintech sector with research proposals. Facilitation of

the development of the network.

Start Date 2023-06-16 09:00:00 End Date 2023-06-16 17:00:00 Duration 1 day Attendance Type Virtual

Total number of expected participants

100 Number of participants

0

expected to be

reimbursed from COST

funds

Daily allowance (EUR) 0.00 Average number of daily

2

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

0.00

0.00

0.00

100 Local Organiser Support (EUR)

500.00

500.00

Title of the Meeting Machine Learning, Artificial Intelligence and Data Protection in Fintech Conference WG1, WG2, CG

Meeting Type(s) Core Group Meeting,Working Group Meeting

Grant Period Goal(s) it will address

Involve associations with a diversity focus,Involve policy makers and disseminate results to them,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description The meeting will take place in hybrid form from Dublin. During the meeting the core group will discuss the ongoing preparation for contributing towards informing

policy at an EU level regarding the development of AI for Fintech with a particular

focus on developing AI Models and XAI that adhere to the GDPR. It will take into

consideration the outputs from the meeting in Brussels in May (COST FinAI -

Fintech and AI in Finance - Policy implications) and expand on them. Additionally,

the working groups will continue to collaborate to ensure the publication of joint

papers across the network and work on the deliverables of the action that are

related to the objectives of each WG. The conference will invite all WG members

to present their research. The event will be hybrid, including face-to-face events in

Dublin and the option to attend online. 2 days with: · 1 plenary sessions of the

Core group – 2h · 1 plenary session for Policy group – 3 h · 1 plenary session for

WG1 – 2h · 1 plenary session for WG2 – 2h · 1 plenary session for WG2 – 2h · 1

plenary session – meeting with members from the Irish FinTech Sector – 2h The

primary objective of this meeting is to inform and advance Fin-AI’s policy agenda

The core group members will discuss the on-going status of the Action. They will

look at the progress regarding the deliverables and construction of GP3 report.

WGs meetings will take place to review the achievements of the group, working on the WG’s reports and strategy for GP4. The conference will present the working

research of the members of most of the WGs with a view to enhancing

cooperation and exchange of ideas.

13

Output(s) A policy paper around AI and data protection policy, which will satisfy the 7th deliverable of the Action (allocated to WG1 and WG2) for providing position

papers, aimed at regulators and policy-makers, on methodology (with examples of

formal criteria) for testing AI techniques in real-time will be finished. A dedicated

website will make the presentations and results available. Substantial transfer of

knowledge from experienced researchers to PhD students (and vice versa) who

will have travelled from numerous COST countries (at least 5 countries). We

expect a long-lasting effect on social interactions from this kind of event. Improved

understanding of academic state-of-the art in AI for Finance, training slides,

presentation slides and new research challenges for ML in Finance developed by

participants available on the Action website.

Location Dublin (Ireland) ITC No Start Date 2023-07-06 14:00:00 End Date 2023-07-07 17:00:00 Duration 2 days Attendance Type Hybrid

Total number of expected participants

40 Number of participants

8

expected to be

reimbursed from COST

funds

Daily allowance (EUR) 211.00 Average number of daily

3

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

420.00

1,053.00

8,424.00

40 Local Organiser Support (EUR)

9,424.00

1,000.00

Title of the Meeting Nordic AI and Fintech

Meeting Type(s) Core Group Meeting,Working Group Meeting

Grant Period Goal(s) it will address

Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions,Paper on testing AI techniques,Publications on investment and hedging strategies on cryptos/digital assets and on traditional assets accounting for ESG criteria,Annual report on the COST Action,Edited volume containing achievements

Description The meeting would take place in a hybrid form in Helsinki. During the meeting the working group will discuss the ongoing preparation of joint publications and work

on the deliverables of the action that are related to the objectives of WG2. WG2

members will also present some of their research. day 1 WG meeting discussing

ongoing activities 3 hours CG meeting discussing action activities 3 hours 2nd day

CG future activity planning and discussion 2 hours WG presentations of research

and ongoing papers 2 hours CG and WG working on deliverables and objectives 3

hours Support, taking COST FinAI contributions into account, will be prioritised: 1)

young researchers from ITC 2) ITC 3) young researchers non-ITC. Senior

researchers from non-ITC are expected to use their own travel funds.

Output(s) The output of the meeting will be the progress on the action deliverables and the joint publications of the WG. In particular, deliverable 6 Methodological discussion

paper on the design of stress tests for the evaluation of AI and ML models under

shifting financial conditions to improve the robustness of models will be done.

Location Helsinki (Finland) ITC No Start Date 2023-07-10 09:00:00 End Date 2023-07-11 17:00:00 Duration 2 days Attendance Type Hybrid

14

Total number of expected participants

40 Number of participants

12

expected to be

reimbursed from COST

funds

Daily allowance (EUR) 207.00 Average number of daily

3

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

400.00

1,021.00

12,252.00

40 Local Organiser Support (EUR)

13,252.00

1,000.00

Title of the Meeting COST FinAI - Fintech and AI in Finance - MC, WG and Core group meeting Meeting Type(s) Core Group Meeting,Management Committee Meeting,Working Group Meeting

Grant Period Goal(s) it will address

Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions,Publications that tackle the issue of diversity in AI and Fintech,Finishing ongoing publications (datathon, financial literacy and women in editorial board of financial papers),Involve associations with a diversity focus,Annual report on the COST Action,Edited volume containing achievements,Involve policy makers and disseminate results to them,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description During the Core Group meeting (approx. 0.5 days) the report to the MC about the Action status will be prepared. Special focus will be given to catching up on the

deliverables for GP3 and how the budget was spent. The WGs will meet on day 2

(approx. 1 day) to discuss their tasks and upcoming outputs and then report to the

plenary (2h). WG1 will focus on blockchain and cryptocurrencies. WG2 will report

on the joint paper initiatives. WG3 will focus on the deliverables related to

transparency of investment products. WG2 will agree on the review and discuss

how to attract participation. All three WGs will also brainstorm on their societal

impacts. The MC (approx. 0.5 days) on day 3 will discuss the progress made

during GP3 and the upcoming grant period 4. The afternoon of day 3 is dedicated

to research presentations of all 3 WGs as well as invited guest speakers. Core

group members are not eligible for reimbursement for the MC meeting. Any travel

reimbursement, even if a COST invitation was sent, is conditional on enough

budget being available at the end of GP3. Support, taking COST FinAI

contributions into account, will be prioritised: 1) young researchers from ITC 2)

ITC 3) young researchers non-ITC. Senior researchers from non-ITC are expected

to use their own travel funds. In case of budget restrictions, travel reimbursement

is limited to one MC member by country. Travel reimbursement is also conditional

on accepting the e-COST invite within 14 days of issuance. Bern Business School

will cover the reimbursement of up to 10k EUR additionally (including Swiss

mobility grants (SEMP. EU equivalent for Erasmus+)). Participants are

encouraged to first use Swiss Mobility grants that Bern Business School can

provide to a few universities.

Output(s) Draft progress report for GP3. Draft Work and Budget Plan for GP 4. Draft objectives for GP4. Draft plans for improving outreach and impact of all WGs. A

dedicated website will make the presentations of day 3 and the results available.

We expect a long-lasting effect on social interactions from this kind of event. New

research challenges for ML in Finance developed by participants available on the

Action website. Deliverable 14. An edited volume containing scientific

achievements of the Action will be set up.

Location Bern (Switzerland) ITC No 15

Start Date 2023-09-27 09:00:00 End Date 2023-09-28 17:00:00

Duration 2 days Attendance Type Hybrid

Total number of expected participants

120 Number of participants expected to be

reimbursed from COST

funds

39

Daily allowance (EUR) 209.00 Average number of daily

3

allowances per participant

Average Long-Distance Costs (EUR)

Average reimbursement (per participant) (EUR)

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Total cost of the meeting (EUR)

400.00

1,027.00

40,053.00

120 Local Organiser Support

(EUR)

41,053.00

16

1,000.00

Training Schools

Overview

Title of the Training School

Dates Location ITC Total Cost (EUR)

COST FinAI Training school Data science for sustainable

economics and

finance

COST FinAI -

Fintech and AI in Finance - Training School for the latest technologies and upcoming

challenges

20/02/2023 - 24/02/2023

26/04/2023 - 28/04/2023

Berlin (Germany) No 7,688.00 Tirana (Albania) Yes 15,950.00

COST FinAI -

Fintech and AI in Finance - Training School on current state-of-the-art and future challenges - Risks and Digital A

19/06/2023 - 23/06/2023

Enschede

(Netherlands)

No 17,660.00

Advanced Statistical Modelling for

Fintech, financial inclusion and

inequality (AFFINE) Details

13/09/2023 - 15/09/2023

Naples (Italy) No 17,296.00 Total 58,594.00

Title of the Training

School

Grant Period Goal(s) it will address

COST FinAI Training school Data science for sustainable economics and finance

Paper on testing AI techniques,Publications on investment and hedging strategies on cryptos/digital assets and on traditional assets accounting for ESG criteria,Involve associations with a diversity focus,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

17

Description The Training School in Berlin is targeted at students and young researchers and all interested in the contemporary topic of sustainable finance, more specifically

(Measuring climate risk for financial applications). The instructors will be mainly

selected from the Action and across all working groups. The participants of this

School will learn the main challenges and solutions in the field of sustainable

finance: incorporation of climate risks to stress-testing, risk scores, climate value

at-risk. Plan: We will invite Students from Ukraine from university funds.

Established researchers will be expected to use their own travel funds, especially

from non-ITC countries. Hybrid; 5 days, each day 3 hours in the morning and 3

hours in the afternoon Monday morning - Arrival and welcome; Monday afternoon

Tuesday morning - lectures from invited speakers (academy and industry);

Tuesday Afternoon - Introduction to the Project (Dataset, tasks) Wednesday,

Thursday Morning - Work in groups on projects Thursday afternoon - Social event

(Preliminary: tour to the industry) Friday morning: Presentations and discussion of

Projects’ results, evaluation.. Wednesday afternoon: Social event Tuesday

morning, Thursday morning: Mini-workshop Friday afternoon: feedback, wrap-up

Preliminary lectures topics: Introduction to data-based mathematical modelling,

introduction to data science, introduction to topics in sustainable finance,

Programming in R & Python (with focus on stat finance), industry talks from

financial institutions on motivation of climate risk modelling for investment projects.

All payment is conditional on trainers to come from at least 5 different COST

countries, which each contributing substantially. Support, taking COST FinAI

contributions into account, will be prioritised: 1) young researchers from ITC 2)

ITC 3) young researchers non-ITC. Senior researchers from non-ITC are expected

to use their own travel funds. Students that are provided housing by the university

will have the daily allowance reduced by 60%.

Output(s) Results will be presented on a dedicated website. Knowledge transfer from experienced researchers to students (and vice versa). long-lasting effect on social

interactions due to planned activities. Improved understanding of FinTech issues

Newsletter of FinAI Webpage on WG1 fin-ai.

Location Berlin (Germany) ITC No Start Date 2023-02-20 09:00:00 End Date 2023-02-24 17:00:00 Duration 5 days Attendance Type Hybrid Participant information Trainers Trainees • Daily allowance (EUR) 212.00 212.00

• Average number of daily allowances per participant

6 6

• Average Long-Distance Costs (EUR) 400.00

• Average reimbursement (EUR) 1,672.00 1,672.00 • Total number of expected trainers/trainees 10 10

• Trainers/trainees expected to be reimbursed from COST funds

2 2

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Local Organiser Support (EUR)

Total cost of the Training School (EUR)

Title of the Training School

6,688.00

10

1,000.00

7,688.00

COST FinAI - Fintech and AI in Finance - Training School for the latest technologies and upcoming challenges

18

Grant Period Goal(s) it will address

Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions,Paper on testing AI techniques,Presentations and dissemination of research results on backtesting investment strategies, performance explanation/attribution and synthetic data generation,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description 3 day doctoral training school on COST topics. The challenges of Fintech and Artificial Intelligence in Finance will be highlighted for young researchers as well as others interested in the subject during this Training School. It will also cover the

most recent research on how to improve it, with a particular focus on extending it

towards Smart Financial services. The future of finance and digital finance will be

discussed with other experts. Students will learn about the problems and potential

solutions in this subject, as well as the most modern AI approaches, their

shortcomings, and new applications, using the MoU of this Action as a practical

example. All payment is conditional on organizers to be from 5 COST countries

and trainers to come from at least 5 different COST countries, that contribute at

least 60%, with each country at most 20%. Support, taking COST FinAI

contributions into account, will be prioritised: 1) young researchers from ITC 2)

ITC 3) young researchers non-ITC. Senior researchers from non-ITC are expected

to use their own travel funds.

Output(s) The presentations and results will be made available on a web portal. Significant information transfer from participants. Long lasting impact on social relations.

Enhanced knowledge for the latest technologies and upcoming challenges.

Increasing the interest of scientific researchers in the field of Fintech and AI in

Finance. Deliverable 10 will be finished.

Location Tirana (Albania) ITC Yes Start Date 2023-04-26 09:00:00 End Date 2023-04-28 14:00:00 Duration 3 days Attendance Type Hybrid Participant information Trainers Trainees • Daily allowance (EUR) 180.00 180.00

• Average number of daily allowances per participant

4 4

• Average Long-Distance Costs (EUR) 430.00

• Average reimbursement (EUR) 1,150.00 1,150.00 • Total number of expected trainers/trainees 10 40

• Trainers/trainees expected to be reimbursed from COST funds

7 6

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Local Organiser Support (EUR)

Total cost of the Training School (EUR)

Title of the Training School

14,950.00

20

1,000.00

15,950.00

COST FinAI - Fintech and AI in Finance - Training School on current state-of-the art and future challenges - Risks and Digital A

19

Grant Period Goal(s) it will address

Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions,Presentations and dissemination of research results on backtesting investment strategies, performance explanation/attribution and synthetic data generation,Publications on investment and hedging strategies on cryptos/digital assets and on traditional assets accounting for ESG criteria,Annual report on the COST Action,Edited volume containing achievements,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description This Training School will highlight to young researchers but also to others interested in the topic, the challenges of Fintech and Artificial Intelligence in

Finance and will discuss the latest findings on how to improve it, with a special

focus on extending this towards Digital Finance. The trainers will be mainly

selected from the Action, across all working groups. Additional expertise will be

invited to discuss the future of Finance, related to Digital Finance. Using the MoU

of this Action as a hands-on example, trainees will learn to understand both

challenges and solutions in this field, to learn most recent AI techniques and their

short-comings as well as recent applications. Financial support will be provided to

PhD students, with priority to improve gender balance and for students from ITC

countries. Established researchers will have to use their own travel funds,

especially from non-ITC countries. Hybrid; 5 days, each day 3 hours in the

morning and 3 hours in the afternoon Monday morning, Tuesday Afternoon,

Wednesday morning, Thursday afternoon: PhD sessions Monday afternoon:

Invited guest lectures Wednesday afternoon: Social event Tuesday morning,

Thursday morning: Mini-workshop Friday morning: Summary, feedback, wrap-up

Support, taking COST FinAI contributions into account, will be prioritised: 1) young

researchers from ITC 2) ITC 3) young researchers non-ITC. Senior researchers

from non-ITC are expected to use their own travel funds.

Output(s) The event brings together member of the cost action and also contributes to the following MoU objectives: by including participants from different areas and

disciplines, and involve possibly new members currently outside the CA19130

network, by organising a session dedicated to ECI and PhD students to receive

feedback by discussants and the audience, Geographical, age and gender

balance will be taken into account when accepting PhD students. A position paper

and roadmap on mitigating risks connected with the increased use of digital

assets A dedicated website will make the presentations and results available.

Substantial transfer of knowledge from experienced researchers to PhD students

(and vice versa). We expect a long-lasting effect on social interactions from this

kind of event. Improved understanding of academic state-of-the art in AI for

Finance, training slides, presentation slides and new research challenges for ML

in Finance developed by participants available on the Action website. Deliverable

11 for GP3 will be done after the event.

Location Enschede (Netherlands) ITC No Start Date 2023-06-19 09:00:00 End Date 2023-06-23 17:00:00 Duration 5 days Attendance Type Hybrid Participant information Trainers Trainees • Daily allowance (EUR) 211.00 211.00

• Average number of daily allowances per participant

6 6

• Average Long-Distance Costs (EUR) 400.00

• Average reimbursement (EUR) 1,666.00 1,666.00 • Total number of expected trainers/trainees 10 15

• Trainers/trainees expected to be reimbursed from COST funds

5 5

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

16,660.00

25

20

Local Organiser Support (EUR)

Total cost of the Training School (EUR)

Title of the Training

School

Grant Period Goal(s) it will address

1,000.00 17,660.00

Advanced Statistical Modelling for Fintech, financial inclusion and inequality (AFFINE)

Publications on investment and hedging strategies on cryptos/digital assets and on traditional assets accounting for ESG criteria,Publications that tackle the issue of diversity in AI and Fintech,Involve associations with a diversity focus,Annual report on the COST Action,Edited volume containing achievements,Involve policy makers and disseminate results to them,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description The Training School in Advanced Statistical Modelling for Fintech, financial inclusion and inequality is offered by University of Naples Federico II and is hosted

by the Laboratory for Statistical Data Analysis within the Department of Political

Science, University of Naples Federico II in September 2023 (13, 14, 15). The

School is designed for COST members, stakeholders, researchers, PhD students,

and possibly brilliant MSc graduates / final-year students interested in Statistics,

Probability, Computer Science, Applied Mathematics, and related areas.The

trainers have been selected from the Action, across all working groups. Among

participants the school will aim at a 50% gender representation and include

members from at least 5 different countries, including ITC members. Preliminary

availability by Albania, Bulgaria, France, Greece, Italy, Ireland, Romania, Turkey,

Macedonia. The aim of the Training School (TS) AFFINE is to establish a track of

high level courses on advanced and cutting-edge topics in Statistics and

Probability with application in FinTech and Artificial Intelligence area. Expertise

and regulators will be invited to discuss the future of Finance, related to Digital

Finance. Participants will learn to understand both the challenges and solutions in

this field, learn about numeracy related to the latest AI techniques, as well as the

latest applications. The School offers lectures delivered by internationally leading

scholars, selected from the Action, across all working groups, on the specific

designated topic, and supervised tutorials. During the school participants analyse

the results of a survey on ‘Knowledge and use of Fintech products’ administered

as part of the CA19130 Action from September to December 2022 and discuss

them also with end-user organisations. One of the objectives is to analyse data

and assess the presence of diversity and inclusion in the fintech area through

appropriate statistical models. Financial support will be provided to PhD and MSc

graduates / final-year students, with priority to improve gender balance and for

students from ITC countries. Established researchers with their own travel funds

can join the Training School without reimbursement by the Action. Training school

for researchers, PhDs and Master students. We will invite trainers and

participants. 3 workshops delivered by internationally leading scholars (3h each)

on a dedicated topic with implementations in our COST Action area will be given.

Two Lab sessions (3h each) show how to repeat the results presented in the

theoretical sessions through the use of open source software. One afternoon is

dedicated to special training on transferable skills. One afternoon for social

networking. A welcome event with a poster session where participants may show

their research activity will also be provided. The event allows an exchange of

information on activities even by those who are not currently part of the action.

Last day is also dedicated to receive input from regulators (Bank of Italy) and

practitioners' communities and to validate results with regard to increasing

transparency of artificial intelligence and Fintech applications (obj 3; 15 - overall

objectives). All payment is conditional on trainers to come from at least 5 different

COST countries, that contribute at least 60%, with each country at most 20%.

Travel reimbursement is restricted to COST members with significant contributions

to the meeting or the Action.

21

Output(s) To introduce participants to statistical models for analysing complex data structures from large-scale surveys consisting of multiple-choice items. Present

parametric and non-parametric frameworks, joint methods for dimension reduction

and clustering, statistical learning for fintech data science, data integration, data

pre-processing and data fusion enhancing participants' understanding. A

discussion paper for possible approaches to building a statistically valid back

testing framework is one of the deliverables (see point 5 GP3 - Overall

deliverables). Methodological discussion papers on AI models to generate “failed

trials” of investment product producers and on quantitative strategies with the

usage of the promising field of network data analysis exchanges and regional

consolidation platforms optimised for accessibility to all partners represent another

AFFINE deliverable (see point 10 GP3 - Overall deliverables). Course slides and

new solutions from open-source software packages, also developed by

participants, will be available on the Action website. Key software (codes,

packages) in line with WG objectives will be developed (see point 12 GP3 -

Overall deliverables). The COST FinAI website will make the presentations and

results available. Substantial transfer of knowledge from experienced researchers

to PhD/master students (and vice versa). We expect a long-lasting effect on social

interactions from this kind of event. Improved understanding of academic state-of

the art in AI for Finance, training slides, presentation slides and new research

challenges for ML in Finance developed by participants available on the Action

website. Materials (slides, data, codes) about TS AFFINE will be updated on the

Action website. Deliverable 5 and 10 will be done at the end of the event.

Location Naples (Italy) ITC No Start Date 2023-09-13 14:00:00 End Date 2023-09-15 17:00:00 Duration 3 days Attendance Type Hybrid Participant information Trainers Trainees • Daily allowance (EUR) 201.00 201.00

• Average number of daily allowances per participant

4 4

• Average Long-Distance Costs (EUR) 360.00

• Average reimbursement (EUR) 1,164.00 1,164.00 • Total number of expected trainers/trainees 10 20

• Trainers/trainees expected to be reimbursed from COST funds

7 7

Total Travel,

Accommodation and Subsistence Costs (EUR)

Total unique participants to be accounted for LOS grant

Local Organiser Support (EUR)

Total cost of the Training School (EUR)

16,296.00

30

1,000.00

17,296.00

22

Mobility of Researchers and Innovators

Grant

Period

Goal(s) it will

address:

Research on backtesting frameworks, digital assets and evalutaion of AI models under shifting financial conditions,Paper on testing AI techniques,Presentations and dissemination of research results on backtesting investment strategies, performance explanation/attribution and synthetic data generation,Publications on investment and hedging strategies on cryptos/digital assets and on traditional assets accounting for ESG criteria,Publications that tackle the issue of diversity in AI and Fintech,Finishing ongoing publications (datathon, financial literacy and women in editorial board of financial papers),Involve associations with a diversity focus,Annual report on the COST Action,Edited volume containing achievements,Involve policy makers and disseminate results to them,Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public

Description: STSMs will be strictly allocated only if the outcome is completion of a deliverable or objective that is not yet finished or achieved. That is in particular deliverable 3 and 5 and additional ones, as decided by the Grant Award Coordinator in cooperation with the Action Chair. Preference will be given to junior researchers and ITC countries. Proof of travel costs has to be provided. Daily allowance is limited to 160 EUR/ day with potential adjustments in line with the EU country coefficients as applied in the HE programme. Virtual grants are only awarded if they directly lead to the completion of a deliverable or objective. Diversity is taken into account. Deadlines will be every month on the 15th, response until the end of the month, mission from the next month onwards. All VGs need to be done jointly by at least 5 COST countries, with each country having a substantial contribution.

Budget (EUR)

Short Term Scientific Missions (STSM) grants 14,000.00

This budget would allow for approx. 7 STSM grants (based on the average costs per STSM grant spent by all Actions).

Virtual Mobility grants 29,300.00

This budget would allow for approx. 20 Virtual Mobility grants (based on the average costs per VM grant spent by all Actions).

Total 43,300.00 23

Presentations at Conferences organised by Third Parties

Description: Our COST Action regularly gets invited to high-level industry, academic and policy meetings. We will disseminate the results of our Action there.

Budget (EUR)

ITC Conference grants 0.00

This budget would allow for approx. 0 ITC Conference grants (based on the average costs per ITC Conference grant spent by all Actions).

Dissemination Conference grants 2,000.00

This budget would allow for approx. 2 Dissemination Conference grants (based on the average costs per DC grant spent by all Actions).

Total 2,000.00 24

Dissemination and Communication Products Overview

Dissemination and Communication Product Title Total Cost (EUR) Action Website Website improvement 2,500.00 Total (without VAT) 2,500.00

Details

Dissemination and

Action Website

Communication Product:

Title: Website improvement

Description: Continous updates and improvements of the website. Budget higher than 1.5k EUR, since so far we have not spent anything on the website.

Total (EUR):

2,500.00

(without VAT)

25

Powered by TCPDF (www.tcpdf.org)