dDeadline Sept 18.

Hard deadline Sept 22.

Deliverables

https://docs.google.com/spreadsheets/d/1U5NKYGEd0zdBin_VXwjllIhV7W2g-YYOklkHbI_Xt-A/edit#gid=1644595933

# Default sentence

Reimbursement is restricted to members with active contributions to the Action and country progress reports in the past. For new members significant contribution to the event is sufficient. Reimbursement is capped if the global budget is not sufficient. Travel cost and LOS reimbursement is conditional on providing the mentioned deliverable/ objective.
Established researchers will be expected to use their own travel funds, especially from non-ITC countries.

# Proposed activities

COST FinAI __Tentative_Proposed_Activities

Contact email:

3 sentences

1.Description

1.1. How the networking activity serves the MoU objectives;

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

1.3. The plans and objectives of the activity

1.4. How the activity serve towards the achievement of the MoU objectives;

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

4. Face to face, hybrid, virtual?

5. Start date and time

6. End date and time

7. City

8. Country

9. Total number of expected participants

10. Requested Local organizer support

11. Number of participants to be reimbursed for travel

For summer schools, in addition:

12. Number of trainers

13. Number of trainees

For STSMS and VGs, only:

1. Description

Please describe here, how the Mobility of Researchers and Innovators shall be implemented by the Action (for example the scientific priorities of the addressed Working Group(s), how the COST Principles will be addressed, type and number of calls for applications etc.)

2. Title of meeting

3. Face to face, hybrid, virtual?

4. Start date and time

5. End date and time

6. City

7. Country

8. Number of trainers

9. Number of trainees

# MoU Objectives

| 1 | Research Coordination 1 | To develop blended approaches to evaluate innovative financial services and their providers, especially in the FinTech domain, building on Machine Learning methods, focussing on prediction (early warning) of operational fragility, fraudulent and illegal behaviour ranging from appropriation of loaned funds to money-laundering activities. |  |
| --- | --- | --- | --- |
| 2 | Research Coordination 2 | The development of conceptual and methodological tools for establishing when black-box models are admissible and, to the extent possible, making them more transparent and/or replacing them with interpretable and explainable models. |  |
| 3 | Research Coordination 3 | To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications. |  |
| 4 | Research Coordination 4 | Pruning and improvement of the vast array of performance attribution models by contributing to the development of methodologies for reducing the false discovery rate in financial research and applied financial investment management. |  |
| 5 | Research Coordination 5 | Disseminate to the public and share with regulators the results on investment product performance evaluation. |  |
| 6 | Research Coordination 6 | Creation of the first European platform comparing the out-of-sample performance of banks' investment products, insurance-linked investment products and asset management products available to the general public. |  |
| 7 | Capacity Building 1 | Create an excellent network of researchers in Europe with lasting collaboration beyond the lifetime of the Action. |  |
| 8 | Capacity Building 2 | Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results. |  |
| 9 | Capacity Building 3 | Bridging the gap between practitioners from the finance industry, academics and regulators by setting up a common knowledge exchange platform. |  |
| 10 | Capacity Building 4 | Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry. |  |
| 11 | Capacity Building 5 | Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility. |  |
| 12 | Capacity Building 6 | Overcome the siloing of research topics by country and achieve geographical and demographical diversity, with special attention to COST Inclusiveness Target countries. |  |
| 13 | Capacity Building 7 | Prepare competitive European researchers for a fruitful career in an international environment through intensive use of Short Term Scientific Missions (STSM) and joint educational programs with industrial partners. |  |
| 14 | Capacity Building 8 | Maximize the job opportunities for PhD students and Early Career Investigators. |  |
| 15 | Capacity Building 9 | Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public. |  |
| 16 | Capacity Building 10 | Significantly improve the gender equality in the fields of the Action. |  |

START HERE AND COPY THE Questions from above

# GP 2 done Oleg Deev - FinAI workshop in Brno

COST FinAI __Tentative_Proposed_Activities

Contact email: oleg@muni.cz

1.Description

3 sentences

Core group meeting. to discuss current status of MoU and GP3 achievements. The event will be hybrid to ensure maximum participation

1.1. How the networking activity serves the MoU objectives;

The networking activity therefore contributes to the following MoU objectives

Obj. 3 - Research Coordination 3 - To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications.

Obj. 8 - Capacity Building 2 - Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

AND

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

→ by including participants from different areas and disciplines, and involve possibly new members currently outside the CA19130 network

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility. → by providing an award (non-monetary) to the best ECI paper presented by a CA19130 member, awarded by the scientific committee during the conference

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators. → by organising a session dedicated to ECI and PhD students to receive feedback by discussants and the audience

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid

1st day afternoon → core group meeting (??? hours) and conference presentations

2nd day → WG meetings (4 hours)

1.3. The plans and objectives of the activity

Core group meeting:

The core group meeting will focus on the deliverables of this Action:

• Transparency in Fintech

• Transparent versus Black Box Decision-Support Models in the Financial Industry

• Transparency into Investment Product Performance for Clients

• Fintech

• Artificial Intelligence in Finance

1.4. How the activity serve towards the achievement of the MoU objectives;

The event brings together member of the cost action and also contributes to the following MoU objectives

Obj. 8 - Capacity Building 2 - Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

AND

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

→ by including participants from different areas and disciplines, and involve possibly new members currently outside the CA19130 network

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility. → by providing an award (non-monetary) to the best ECI paper presented by a CA19130 member, awarded by the scientific committee during the conference

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators. → by organising a session dedicated to ECI and PhD students to receive feedback by discussants and the audience

According to the objectives in terms of diversity, the organisation will fulfill these requirements whenever possible

Geographical, age and gender balance will be addressed as follows:

- All activities are monitored and prioritised based on wide geographical inclusion and distribution across Europe

- Our networking tools will reserve at least 50% of the funds for Early Career Investigators.

- Gender balance is one of our goals and we will actively promote female participants in all our activities. Preferences, given the same qualifications, will be given to female researchers. We actively aim to increase our female participation to 50% throughout the Action.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/fintech_ai_in_finance/events/289106947/)

MeetUp

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from industry and policy makers.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

Abstracts of papers presented could be made available online on the website of the event (upon permission by authors)

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

Brno Workshop on Artificial Intelligence in Finance

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

21 October 2022, 13.00 CET

6. End date and time

22 October 2022, 13.00 CET

7. City

Brno

8. Country

Czechia

9. Total number of expected participants

10

10. Requested Local organizer support

1000 euro

11. Number of participants to be reimbursed for travel

10

# 2 Alessandra Tanda Pavia Diversity

Contact email: alessandra.tanda@unipv.it

Check list

- Special issues

- Deliverables/ Objectives completed → Deliverable 2. A database which contains data on crowdfunding/P2P platform features useful for rating platform integrity and to predict fraud

Deliverable 15. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36 ) → discussion of stakeholders engagement in the Action and new activities in light of the revision in month 36

- High-quality event, also potentially for continuation (show evidence that it previously was a successful event)

Last year ECI award on behalf of Cost Fin-AI was given to A. Citterio, now member of Cost Action for his paper “The role of artificial intelligence in supporting environmental transition/finance” currently published in amended form in Finance Research Letters (https://www.sciencedirect.com/science/article/pii/S1544612322005888) with COST acknowledgment

4.    Joint events with working group meetings.

We have core group meeting, diversity meeting and policy meeting scheduled on the days

5.    Check if we have separate working group meetings and have at least two working groups together

6.    Policy makers should be involved, i.e. wider outreach to others.

One keynote is a policy maker

1.Description

https://www.meetup.com/fintech_ai_in_finance/events/288557097/

Core group meeting to discuss the current status of MoU and GP3 achievements. The event will be hybrid to ensure maximum participation

Diversity meeting to discuss diversity goals and achievements and discuss potential adjustments.

The diversity meeting will focus on these topics

• Women in fintech III conference

• ongoing projects and initiatives by diversity team members (e.g. VMG awarded to diversity team members, research projects run by members, etc.)

• any other issues

2nd COST FinAI workshop on Environmental finance for the common good - Fintech and AI for more sustainable societies: event dedicated to opportunities and obstacles to more inclusive and sustainable societies prompted by Fintech and AI tools applied to finance and investment evaluation in a multidisciplinary setting. Workshop with COST FinAI organizers and speakers (more than 70%)

One session dedicated to PhD students and ECI. Each presenter will be assigned a discussant to get feedback.  The activity hence aims at bringing together academics, early career investigators, phd students, the industry and policy makers to discuss around the issue of sustainability and if and how Fintech applications pose an opportunity or a threat to a more sustainable and more inclusive society. New methodologies that employ artificial intelligence in this area will also be presented and discussed.

1.1. How the networking activity serves the MoU objectives;

The event hosts

- Core group Meeting to discuss current status of MoU and GP3 achievements. The event will be hybrid to ensure maximum participation

- Diversity meeting. Current members of the diversity team include Alessandra Tanda, Alessia Paccagnini, Claudia Tarantola; Alberto Citterio, Maria Iannario, Gemma Marina, Branka Hadji Misheva, Meriem Kerbouche, Petre Lameski, Codruta Mare, Belma Ozturkkal, Tatjana Pacemska, Rezarta Perri, Galena Pisoni, Albulena Shala. This group is made of ECI, women, and researchers from different backgrounds and countries, including ITC. The event will hybrid to ensure maximum participation.

- Policy meeting to discuss shaping of policy at EU level. Dr Maria Moloneyis member of the CEDPO Working Group on Artificial Intelligence and will work towards bringing research results from the COST Action to the CEDPO AI WP as well as working on other areas of policy within the COST Action itself.

- On the same days and venue, members of Cost Action will organise and take part in the second edition of the workshop on Environmental finance for the common good and this edition will be titled “Fintech and AI for more sustainable societies”.  In the same vein of the first edition (see here the details https://efcg2022.sciencesconf.org/) it will bring together academia, industry and policy makers.

Output

Abstracts of papers presented will be made available online on the website of the event (upon

permission by authors)

A selection of papers presented during the conference, relevant to the COST FinAI topics, will be invited for submission in open access journals.

The event will allow interaction among its members during breaks and social events organised; discuss state of the art and future planning to successfully reach CA19130 objectives; Planning of future events by cost diversity team to reach CA19130 objectives in terms of diversity

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid

1st day afternoon → core group meeting (1.5 hours) and conference presentations

2nd day → diversity meeting (1.5 hours) and conference and parallels sessions  (number depending on the number of papers received for presentation)

1.3. The plans and objectives of the activity

Core group meeting:

The core group meeting will focus on the deliverables of this Action:

• Transparency in Fintech

• Transparent versus Black Box Decision-Support Models in the Financial Industry

• Transparency into Investment Product Performance for Clients

• Fintech

• Artificial Intelligence in Finance

Diversity meeting

The diversity meeting will focus on these topics

• Women in fintech III conference

• ongoing projects and initiatives by diversity team members (e.g. VMG awarded to diversity team members, research projects run by members, etc.)

• any other issues

Beside the networking activities planned for the two-day event, there will be a conference session, with plenary sessions and parallel sessions, with one session dedicated to PhD students and ECI. Each presenter will be assigned a discussant to get feedback.

The activity hence aims at bringing together academics, early career investigators, phd students, the industry and policy makers to discuss around the issue of sustainability and if and how Fintech applications pose an opportunity or a threat to a more sustainable and more inclusive society. New methodologies that employ artificial intelligence in this area will also be presented and discussed.

1.4. How the activity serve towards the achievement of the MoU objectives;

The event brings together member of the cost action and also contributes to the following MoU objectives

Obj. 8 - Capacity Building 2 - Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

AND

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

→ by including participants from different areas and disciplines, and involve possibly new members currently outside the CA19130 network

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility. → by providing an award (non-monetary) to the best ECI paper presented by a CA19130 member, awarded by the scientific committee during the conference

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators. → by organising a session dedicated to ECI and PhD students to receive feedback by discussants and the audience

According to the objectives in terms of diversity, the organisation will fulfill these requirements whenever possible

Geographical, age and gender balance will be addressed as follows:

- All activities are monitored and prioritised based on wide geographical inclusion and distribution across Europe

- Our networking tools will reserve at least 50% of the funds for Early Career Investigators.

- Gender balance is one of our goals and we will actively promote female participants in all our activities. Preferences, given the same qualifications, will be given to female researchers. We actively aim to increase our female participation to 50% throughout the Action.

With this respect, the organising committee of the event will aim at a 50% gender representation and include members from at least 5 different countries, including  ITC members. Preliminary availability by Italy, Portugal, Finland, Croatia and Ireland.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

https://www.meetup.com/en-US/fintech_ai_in_finance/events/288557097/

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from industry and policy makers.

2. Output

## 2.1. Codified knowledge, e.g. publications; patents, websites

Abstracts of papers presented will be made available online on the website of the event (upon

permission by authors)

A selection of papers presented during the conference, relevant to the COST FinAI topics, will be invited for submission in open access journals.

The event will allow interaction among its members during breaks and social events organised; discuss state of the art and future planning to successfully reach CA19130 objectives; Planning of future events by cost diversity team to reach CA19130 objectives in terms of diversity

This event will contribute to deliverable 15. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36) by including policy makers, associations, and the industry, and Obj 3.To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications. And Obj 9- Bridging the gap between practitioners from the finance industry, academics and regulators by setting up a common knowledge exchange platform. And Obj 15	Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public.

Deliverable 2. A database which contains data on crowdfunding/P2P platform features useful for rating platform integrity and to predict fraud

Deliverable 15. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36 → discussion of stakeholders engagement in the Action and new activities in light of the revision in month 36

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

The event will also allow interaction among its members during breaks and social events organised

State of the art and future programming to successfully reach CA19130 objectives

Programming of future events by cost diversity team to reach CA19130 objectives in terms of diversity

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

Diversity challenges for a sustainable Fintech

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

13 april, 13.00 CET

6. End date and time

14 April, 18.00 CET

7. City

Pavia

8. Country

Italy

9. Total number of expected participants

40

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

20

__________________________________________________________________________________________________

START HERE AND COPY THE Questions from above

# 4 Alessandra Tanda Women in Fintech III - Portugal

Check list

- Special issues

- Deliverables/ Objectives completed → Obj 15 Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public → make abstracts of papers (and papers, subject to authors’ approval) available on the COST Fin-AI website.

Deliverable 15. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36 → discussion of stakeholders engagement in the Action and new activities in light of the revision in month 36

- High-quality event, also potentially for continuation (show evidence that it previously was a successful event)

2022 Tirana → Women in Fintech II: Tirana and online, 21st-22nd September 2022

We had on site 40 COST participants (19 in day one and 21 in day two), and 6 participants online.

Other non COST participants onsite were about 25 for both days (12 day one and 13 day two). Additionally, we hosted a session with the industry exponents:

11.00 – 12.30 Session 2: CEO Women in Fintech, Best Practices and Challenges for Women in Fintech. Bridging academia with industry. (2nd day)

    - Linda Shomo, CEO of EasyPay, Albania

    - Hanna Kristín Skaftadóttir, CEO of mojoflower.io, Iceland

    - Magda Săndulescu, Executive Director of RoFin.tech (Romanian Fintech Association)

    - Alina Luchian, Education & Academic Program Manager of SAS Romania

    - Aneida Bajraktari Bicja, Co-Founder & CEO - Balkans Capital; Irena Rushaj, Head of IT Department, Union Bank of Albania; Sabi Osmani, CEO & Founder Easy Albania

2021 Online → with more than 20 female speakers and a large audience, in September 2021. Had special issue in Digital Finance https://link.springer.com/journal/42521/volumes-and-issues/4-4

4.    Joint events with working group meetings.

5.    Check if we have separate working group meetings and have at least two working groups together

6.    Policy makers should be involved, i.e. wider outreach to others.

Check with local organisers

Contact email: alessandra.tanda@unipv.it (on behalf of the diversity team)

1.Description

The event is titled Women in Fintech and AI and it is the third edition of the annual event organised by the diversity team of CA19130. The event aims at bringing together academia, industry and policy maker to discuss gender equality and how AI and Fintech pose opportunities and challenges to a more inclusive society

We need 1-3 sentences here

1.1. How the networking activity serves the MoU objectives;

This activity is the third edition of the Women in Fintech and AI conference. The first was organised online by the diversity team and the second in hybrid form, hosted by Tirana university.

The meeting is aimed at raising awareness of the gender gap in Fintech and fostering inclusion of women in the discussion around Fintech and AI.  In particular, it aims at reaching these GP2 objectives

-	Actively seek, encourage and promote research from researchers at different stage of their carriers and females

-	Ensure high quality events and discussions around diversity

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Two-day event

1.3. The plans and objectives of the activity

1.4. How the activity serve towards the achievement of the MoU objectives;

This activity is the third edition of the Women in Fintech and AI conference. The first was organised online by the diversity team and the second in hybrid form, hosted by Tirana university.

The meeting is aimed at raising awareness of the gender gap in Fintech and fostering inclusion of women in the discussion around Fintech and AI.  In particular, it aims at reaching these GP2 objectives

-	Actively seek, encourage and promote research from researchers at different stage of their carriers and females

-	Ensure high quality events and discussions around diversity

It also contributes to these MoU objectives:

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

https://www.meetup.com/en-US/fintech_ai_in_finance/events/288557097/

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

Will be decided together with the local organising committee.

Objective in mind is a gender, geographic and age balance across cost members. At least 5 countries will be involved in the organising committee and speakers.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

Greater awareness of the role of Women in the financial industry and in the technological development

This event will contribute to deliverable 15. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36) by including policy makers, associations, and the industry, and Obj 3.To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications. And Obj 9- Bridging the gap between practitioners from the finance industry, academics and regulators by setting up a common knowledge exchange platform. And Obj 15	Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public.

Obj 15 Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public → make abstracts of papers (and papers, subject to authors’ approval) available on the COST Fin-AI website.

Deliverable 15. Strategy to engage stakeholders in the Action (including revisions in month 24 and 36 → discussion of stakeholders engagement in the Action and new activities in light of the revision in month 36

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

Women in Fintech and AI - IIIrd edition

4. Face to face, hybrid, virtual?

hybrid

5. Start date and time

24 May 2023

6. End date and time

25 May 2023

7. City

Coimbra

8. Country

Portugal

9. Total number of expected participants

40

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

20

# 9 Joerg Osterrieder MC and Core and WG meeting

Grant period goals it will address

To do

Description for Meetup

8th European COST Conference on Artificial Intelligence in Finance

COST FinAI Management, Core group, Working group meetings

Description for COST

During the Core Group meeting (approx. 0.5 days) the report to the MC about the Action status will be prepared. Special focus will be given to catching up on the deliverables for GP3 and how the budget was spent.

The WGs will meet on day 2 (approx. 1 day) to discuss their tasks and upcoming outputs and then report to the plenary (2h). WG1 will focus on blockchain and cryptocurrencies. WG2 will report on the joint paper initiatives. WG3 will focus on the deliverables related to transparency of investment products.

WG2 will agree on the review and discuss how to attract participation.

All three WGs will also brainstorm on their societal impacts.  The MC (approx. 0.5 days) on day 3 will discuss the progress made during GP3 and the upcoming grant period 4.

The afternoon of day 3 is dedicated to research presentations of all 3 WGs as well as invited guest speakers.

Output:

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from industry.

2. Output

Draft progress report for GP3. Draft Work and Budget Plan for GP 4. Draft objectives for GP4.
Draft plans for improving outreach and impact of all WGs.
A dedicated website will make the presentations of day 3 and the results available.
We expect a long-lasting effect on social interactions from this kind of event.
New research challenges for ML in Finance developed by participants available on the Action website.

3. Title of meeting

8th European COST Conference on Artificial Intelligence in Finance

COST FinAI - Fintech and AI in Finance - MC, WG  and Core group meeting

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

Sept 27, 9am

6. End date and time

Sept 29, 5pm

7. City

Bern

8. Country

Switzerland

9. Total number of expected participants

120

10. Requested Local organizer support

6000

11. Number of participants to be reimbursed for travel

80

# 5 Joerg Osterrieder Training School Twente

Contact email: joerg.osterrieder@bfh.ch

1.Description

This Training School will highlight to young researchers but also to others interested in the topic, the challenges of Fintech and Artificial Intelligence in Finance and will discuss the latest findings on how to improve it, with a special focus on extending this towards Digital Finance. The trainers will be mainly selected from the Action, across all working groups. Additional expertise will be invited to discuss the future of Finance, related to Digital Finance. Using the MoU of this Action as a hands-on example, trainees will learn to understand both challenges and solutions in this field, to learn most recent AI techniques and their short-comings as well as recent applications.

Financial support will be provided to PhD students, with priority to improve gender balance and for students from ITC countries. Established researchers will have to use their own travel funds, especially from non-ITC countries.

1.1. How the networking activity serves the MoU objectives;

This event will in particular support all capacity building objectives, with a particular focus on young researchers and PhD students: We will bring researchers together (Obj. 8), transfer knowledge (Obj. 10), organise feedback for PhDs from discussants and audience (Obj 14).

To collect and assess potential approaches for improving Transparency in Finance; To increase the contributions of Young Researchers and Innovators from ITC countries compared to last year, while safeguarding gender balance and enhancing diversity in the Action;

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid; 5 days, each day 3 hours in the morning and 3 hours in the afternoon

Monday morning, Tuesday Afternoon, Wednesday morning, Thursday afternoon: PhD sessions

Monday afternoon: Invited guest lectures

Wednesday afternoon: Social event

Tuesday morning, Thursday morning:  Mini-workshop

Friday morning: Summary, feedback, wrap-up

1.3. The plans and objectives of the activity

Training school for PhDs. We will invite trainers and PhDs. Students will present their research and receive feedback from experienced discussants. 2 mini-workshops (3h each) on a dedicated topic related to our COST Action will be given by invited trainers. One afternoon is dedicated to special training on transferable skills & career perspectives. One afternoon for social networking.

1.4. How the activity serve towards the achievement of the MoU objectives;

The event brings together member of the cost action and also contributes to the following MoU objectives: by including participants from different areas and disciplines, and involve possibly new members currently outside the CA19130 network, by organising a session dedicated to ECI and PhD students to receive feedback by discussants and the audience,  Geographical, age and gender balance will be taken into account when accepting PhD students.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

COST Countries Involved

Romania, Codruta Mare, Ioana

Switzerland, Branka Hadji Misheva

Netherlands, Joerg Osterrieder

Austria, Ronald Hochreiter

North Macedonia, Petre Lameski

Ireland, Valerio Poti

2. Output

Deliverables:

A position paper and roadmap on mitigating risks connected with the increased use of digital assets

A dedicated website will make the presentations and results available.

Substantial transfer of knowledge from experienced researchers to PhD students (and vice versa).

We expect a long-lasting effect on social interactions from this kind of event.

Improved understanding of academic state-of-the art in AI for Finance, training slides, presentation slides and new research challenges for ML in Finance developed by participants available on the Action website.

3. Title of meeting

COST FinAI - Fintech and AI in Finance - Training School on current state-of-the-art and future challenges - Risks and Digital Assets

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

June 19, 9am

6. End date and time

June 23, 5pm

7. City

Enschede

8. Country

Netherlands

9. Total number of expected participants

40

10. Requested Local organizer support

10000

11. Number of participants to be reimbursed for travel

30

# 3 Joerg Osterrieder Policy Meeting Brussels, WG1-3, CG

Grant period goals it will address

To interact with policy makers; To finalise a policy white paper for our Action; to transfer knowledge from academia to policy-makers;

Description

The Workshop (two full days) shall highlight the findings of the Action as it relates to policy implications. Representatives from the WG will present their findings and put them into context of policy implications.

Policy makers from the EU will be invited to attend and show their point of view and to discuss with Action participants.

Output:

Dissemination of the COST Action results to policy makers, white paper on policy implications of our Action.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

3. Title of meeting

COST FinAI - Fintech and AI in Finance - Policy implications

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

May 8, 1pm

6. End date and time

May 9, 12pm

7. City

Brussels

8. Country

Belgium

9. Total number of expected participants

40

10. Requested Local organizer support

Check with Ralph

11. Number of participants to be reimbursed for travel

30

# 6 Petre Lameski CG and WG2 meeting in Helsinki - (proposer:Petre, Joerg)

https://docs.google.com/spreadsheets/d/1pMeu4BS3vv_mbJ395FG6R3GhObW_Qo1O6vIHH0vkIiY/edit#gid=1395089157

Contact email: lameski@finki.ukim.mk

1. Description

The meeting would take place in a hybrid form in Helsinki. During the meeting the working group will discuss the ongoing preparation of joint publications and work on the deliverables of the action that are related to the objectives of WG2. WG2 members will also present some of their research.

1.1. How the networking activity serves the MoU objectives;

The activity will cover the following objectives of the action:

| Capacity Building 5 | Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility. |
| --- | --- |

| Capacity Building 1 | Create an excellent network of researchers in Europe with lasting collaboration beyond the lifetime of the Action. |
| --- | --- |
| Capacity Building 2 | Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results. |

| Research Coordination 1 | To develop blended approaches to evaluate innovative financial services and their providers, especially in the FinTech domain, building on Machine Learning methods, focussing on prediction (early warning) of operational fragility, fraudulent and illegal behaviour ranging from appropriation of loaned funds to money-laundering activities. |
| --- | --- |
| Research Coordination 2 | The development of conceptual and methodological tools for establishing when black-box models are admissible and, to the extent possible, making them more transparent and/or replacing them with interpretable and explainable models. |

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

The meeting is planned to be in hybrid format. The proposed agenda is as follows:

Day 1:

- WG meeting discussing ongoing activities 3 hours

- CG meeting discussing action activities 3 hours

Day 2:

- CG future activity planning and discussion 3 hours

- WG presentations of research and ongoing papers 3 hours

- CG and WG working on deliverables and objectives

1.3. The plans and objectives of the activity

The goal of this activity is to increase the visibility of young researchers by allowing presentations of work in progress research in front of the action community and enable researchers to receive feedback for their work. Also, during the meetings, the ongoing activities of the action will be assessed and the delegates will work on the current action deliverables and plan for objectives accomplishement.

1.4. How the activity serve towards the achievement of the MoU objectives;

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

TBA

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

The output of the meeting will be the progress on the action deliverables and the joint publications of the WG

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

CG and WG2 meeting in Helsinki

4. Face to face, hybrid, virtual?

hybrid

5. Start date and time

| July 10, 2023 | 9:00 |
| --- | --- |

6. End date and time

| July 11, 2023 | 17:00 |
| --- | --- |

7. City

Helsinki

8. Country

Finland

9. Total number of expected participants

40

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

10-15

# 1 Codruța MARE Diversity + WG 1 + WG2 + Core

Diversity challenges and stakeholders' engagement

Contact email: codruta.mare@econ.ubbcluj.ro, codruta.mare@ubbcluj.ro

1.Description

Description

As this will be the first in person meeting of the Action in 2023, during the Core Group meeting (approx. 2 hours) the status of the Action will be assessed, especially in terms of the objectives and deliverables - what was achieved in GP2 and what is running or has to be achieved in GP3. The Diversity Team will meet after, to assess the diversity report for GP2 and prepare the strategy for GP3, especially to prepare the Women in Fintech III Conference in May 2023, in Coimbra, Portugal. Additionally, a special paper session will be dedicated to presentation of research conducted by the diversity team. WG1 and WG2 will meet in parallel on the 2nd day, to discuss research conducted in each of them, on one hand, and their strategies related to objectives and deliverables, on the other. This meeting is also related to the Action’s Strategy to engage stakeholders - related to this, the status of the strategy’s fulfilment will be assessed and actions to enhance cooperation with the stakeholders will be discussed. For this, the meeting will end with a round table with the representatives of the Romanian FinTech sector and the IT companies working in the field. One of the meeting’s goals is to build the action plan for the construction of the first FinTech report for the Balkans, once again related to the Action’s strategy to engage stakeholders. Additionally, a special session dedicated to PhD students and young researchers will be organized.

MEETUP Link: https://www.meetup.com/fintech_ai_in_finance/events/289867639/?isFirstPublish=true

Output:

Abstracts of presentations will be made available online (upon permission by authors).

Strategies of the Action for GP3 will be monitored in terms of implementation and reporting, along with starting constructing the strategies for GP4. More specifically, participants will work on the diversity strategy, the stakeholders one and the WG1 and WG2 ones. The event will also allow interaction among its members. Societal implications in the Fintech sector with research proposals.

Deliverables:

Substantial transfer of knowledge from experienced researchers to PhD students (and vice versa).

Strategy to engage stakeholders in the Action.

Strategy for diversity.

D8. Report on good examples and best practices for a transparent finance industry with guidelines to improve transparency.

Objectives tackled: 3, 5, 7, 8, 9, 10, 11, 15, 16

Core group meeting

Diversity meeting

WG1 and WG2 meeting

1.1. How the networking activity serves the MoU objectives;

The event will host the Diversity meeting, Core group meeting, along with WG1 and WG2 meetings.

Representatives of the Romanian Fintech Association will be invited to enhance the cooperation with the stakeholders.

The event will focus on two major aspects of CA 19130 activity - diversity and stakeholders’ involvement. It will help participants to actively contribute to the writing of the diversity and stakeholders reports. It will provide a place for members of the Action to actively participate in the strategy construction and implementation related to the two major topics.

Additionally, it also support and facilitates the meeting of WG1 and WG2 members, that have the opportunity to exchange ideas, and to work on the Action’s deliverables.

Participation will be hybrid, to ensure a maximum participation.

It therefore contributes to the following MoU objectives:

Obj. 8 - Capacity Building 2 - Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility.

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators.

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid

2 days with:

·   	1 plenary sessions of the Core group – 2h

·   	1 plenary session for Diversity group – 3 h

·   	1 plenary session for WG1 – 2h

·   	1 plenary session for WG2 – 2h

·   	1 plenary session – meeting with the Romanian FinTech Sector – 2h

1.3. The plans and objectives of the activity

The main goal of the 2-day event is to facilitate the meeting of:

1.      The core group members to discuss the status of the Action, the status of the deliverables and the state-of-the-art of GP3.

2.      The Diversity group meeting to evaluate the achievements of the group, monitor the status of the strategy implementation, talk about the Diversity report for GP2 and strategy for GP3, presentation of the research conducted by the Diversity group members in order to enhance cooperation, preparation for Women in Fintech III.

3.      WG1 and WG2 meetings to evaluate the achievements of the group, and plan the strategy for GP4, presentation of the research conducted by the group members in order to enhance cooperation.

4.      Meeting the Romanian FinTech representatives and the local IT companies working in the field in order to enhance the cooperation with the stakeholders. This will be an opportunity to contribute to the Action’s Strategy to engage stakeholders.

5. Organize a special session dedicated to young researchers and PhD students.

1.4. How the activity serves towards the achievement of the MoU objectives;

The event brings together member of the Cost Action and also contributes to the following MoU objectives

Obj. 8 - Capacity Building 2 - Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

→ by facilitating the cooperation with the stakeholders

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility.

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

Not yet available, meetup will be set up and the event announced through the newsletter of the Action.

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from industry and policy makers.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

Abstracts of presentations will be made available online (upon permission by authors).

Strategies of the Action for GP3 will be monitored in terms of implementation and reporting, along with starting constructing the strategies for GP4. More specifically, participants will work on the diversity strategy, the stakeholders one and the WG1 and WG2 ones. The event will also allow interaction among its members. Societal implications in the Fintech sector with research proposals.

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

The event will also allow interaction among its members.

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

Implication in the Fintech sector with research proposals.

3. Title of meeting

Diversity challenges and stakeholders' engagement

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

1 February 2023 in Cluj-Napoca, Romania

6. End date and time

2 February 2023 in Cluj-Napoca, Romania

7. City

Cluj-Napoca

8. Country

Romania

9. Total number of expected participants

40

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

30

Roman Matkovskyy - The FinTech Rennes-Paris Summer School

Contact email: roman.matkovskyy@rennes-sb.com

1.Description

The FinTech Rennes-Paris Summer School is targeted at students and young researchers and all interested in the contemporary topic of FinTech. The instructors will be will be mainly selected from the Action and across all working groups the Rennes School of Business. The participants of this Summer school will learn the main challenges and solutions in the field of FinTech, e.g., crypto-market, sustainable finance and FinTech etc..

Financial support will be provided to youth, with priority to improve gender balance and for applicants from ITC countries. Established researchers will be expected to use their own travel funds, especially from non-ITC countries.

1.1. How the networking activity serves the MoU objectives;

Overall, this school will support all capacity building objectives, with a particular focus on youth interested in FinTech, young researchers and potential PhD students:

We will bring researchers together (Obj. 8), transfer knowledge (Obj. 10), organise feedback for the participants from discussants and audience (Obj 14).

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid; 5 days, each day 3 hours in the morning and 3 hours in the afternoon

Monday afternoon and Wednesday afternoon: Invited guest lectures

Thursday morning: mini-workshop

Thursday afternoon: Social event

Friday morning: Summary, feedback, wrap-up

1.3. The plans and objectives of the activity

Training school for students and young researchers. We will invite instructors and PhDs. Students will present their research projects and receive feedback from experienced discussants.

Mini-workshops (3h) on a dedicated topic related to our COST Action and FInTech will be given by invited trainers.

One afternoon is planned to have a training on transferable skills & career perspectives.

One afternoon for social networking.

1.4. How the activity serve towards the achievement of the MoU objectives;

The planned summer school brings together FInAI Cost Action members and contributes to the following MoU objectives:

- By involving participants from different areas and disciplines, incl. the potential new members;

- by organising a session dedicated to ECI and PhD students to receive feedback by discussants and the audience;

- Equality is a priority: geography, age and gender balance.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

Not available as of now; meetup will be set up and the event announced through the newsletter of the Action.

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be confirmed. They are the distinguished speakers from CA19130, from other academic institutions, industry and policy makers.

2. Output

Results  will be presented on a dedicated website.

Knowledge transfer from experienced researchers to students (and vice versa).

long-lasting effect on social interactions due to planned activities.

Improved understanding of FinTech issues

3. Title of meeting

COST FinAI - Fintech and AI in Finance - The FinTech Rennes-Paris summer school

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

June 12, 9am (TBC)

6. End date and time

June 16, 5pm (TBC)

7. City

Rennes and Paris

8. Country

France

9. Total number of expected participants

30

10. Requested Local organizer support

10000

11. Number of participants to be reimbursed for travel

30

# Withdrawn Roman Matkovskyy  - Conference/core group/WG meeting

Contact email: roman.matkovskyy@rennes-sb.com

1.Description

Conference

Core group meeting

WG1/WG3/WG3

1.1. How the networking activity serves the MoU objectives;

This event will provide an opportunity for the participants to make an overview of the activities and achievements, setting new goals within MoU and adjusting the strategic plans in reaching the FInAI objectives.

The event will host the Core group meeting, along with WGs meetings.

Guests from French fintech/AI industry will be invited..

Participation will be in a hybrid mode, to ensure a maximum participation.

The event will contribute to the following MoU objectives:

Obj. 8 - Capacity Building 2 - Bringing researchers with different background together, (1) to define future research agenda in an interdisciplinary setting;  (2) to update and extend knowledge on FinTech issues across France and Europe, (3) to disseminate results.

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility.

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators.

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid

2 days with:

·   	1 plenary sessions of the Core group – 2h

·   	1 plenary session for WGs – 4h

·   	1 plenary session – meeting with the French FinTech Sector – 2h

1.3. The plans and objectives of the activity

The main goal of the 2-day event is to facilitate the meeting of:

1.      The core group members to discuss the status of the Action, the status of the deliverables and construction of GP3 report.

2.       WGs meetings to evaluate the achievements of the group, build the WG’s reports and strategy for GP4, presentation of the research conducted by the group members in order to enhance cooperation.

4.      Meeting the French FinTech representatives to enhance the cooperation with the stakeholders.

1.4. How the activity serves towards the achievement of the MoU objectives;

The event brings together member of the Cost Action and also contributes to the following MoU objectives

Obj. 8 - Capacity Building 2 - Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

Obj. 10 - Capacity Building 4 - Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

→ by facilitating the cooperation with the stakeholders

Obj 11 - Capacity Building 5 - Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility.

Obj. 14 - Capacity Building 8 - Maximize the job opportunities for PhD students and Early Career Investigators.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

Not available as of now; meetup will be set up and the event announced through the newsletter of the Action.

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from industry and policy makers.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

Abstracts of presentations will be made available online (upon permission by authors)

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

The event will also allow interaction among its members.

2.3.  Technology: e.g. a prototype, a database;

NA

2.4. Societal applications

Implication in the Fintech sector with research proposals.

Facilitation of the GP3 reports writing.

3. Title of meeting

TBD

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

15 June 2023 – TBD

6. End date and time

16 June 2023 – TBD

7. City

Paris

8. Country

France

9. Total number of expected participants

40

10. Requested Local organizer support

10000

11. Number of participants to be reimbursed for travel

30

# Previous GPeriod Petre Lameski WG 2 meeting in Skopje (2nd Grant period) - (proposer: Petre Lameski)

Contact email: lameski@finki.ukim.mk

We have seen the need to organise additional working group meetings due to the size of the network and the sheer amount of work, output, deliverables. Also, due to Corona, travel was still somehow limited, so we want to give more members the opportunity to meet face to face.

1.Description

The COST Action CA19130 Fintech and AI in Finance is organising an interdisciplinary WG meeting open to all MC and WG members.

During the meeting we will have open discussions regarding the WG objectives and activities. The meeting will be used to discuss the action accomplishments during the past period and consolidate the work of the working groups. The WG meeting will be a joint meeting of all working groups. The meeting will be used to finalise action deliverables and discuss future joint publications and project proposals.

The meeting will directly serve the RCO1 and RCO2 and CB1 and CB5 from the MoU. It will also serve towards finalising deliverables.

1 day hybrid event

https://www.meetup.com/fintech_ai_in_finance/events/288749647?utm_medium=referral&utm_campaign=share-btn_savedevents_share_modal&utm_source=link

1.1. How the networking activity serves the MoU objectives:

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

1.3. The plans and objectives of the activity

1.4. How the activity serve towards the achievement of the MoU objectives;

During the meetings the participants will discuss the ongoing research collaborations within the action and will use the time to jointly work on the action deliverables.

The meeting is planned to be a joint WG meeting for evaluating the action achievements so far and working on the deliverables and the action objectives. The meeting will also be used to plan future inter WG collaboration and joint publications.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

https://www.meetup.com/fintech_ai_in_finance/events/288749647?utm_medium=referral&utm_campaign=share-btn_savedevents_share_modal&utm_source=link

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

None

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

Output will be the proposals for joint publications and deliverables

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST

Output will be the proposals for joint publications and deliverables;

Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

WG meeting in Skopje

4. Face to face, hybrid, virtual?

hybrid

5. Start date and time

10.10.2022 9:00

6. End date and time

10.10.2022 17:00

7. City

Skopje

8. Country

Macedonia

9. Total number of expected participants

20

10. Requested Local organizer support

1000 EUR

11. Number of participants to be reimbursed for travel

10

# 12 Valerio Poti, Alessia Paccagnini and Maria Moloney Core and Work Group Meeting + Training School + Conference

COST FinAI __Tentative_Proposed_Activities

Contact email:  Maria.Moloney@ucd.ie

A conference to include Ethical Artificial Intelligence, Machine Learning (for Microfinance - Alessia), and Data Protection (for AI - Maria) in Fintech as well as preparatory meetings for the policy event we plan to hold in Bruxelles

1.Description

The meeting will take place in hybrid form from Dublin. During the meeting the core group will discuss the ongoing preparation for contributing towards informing policy at an EU level regarding the development of AI for Fintech with a particular focus on developing AI Models and XAI that adhere to the GDPR. It will take into consideration the outputs from the meeting in Brussels in May (COST FinAI - Fintech and AI in Finance - Policy implications) and expand on them.

Additionally, the working groups will continue to collaborate to ensure the publication of joint papers across the network and work on the deliverables of the action that are related to the objectives of each WG. The conference will invite all WG members to present their research.

1.1. How the networking activity serves the MoU objectives;

The following MoU would be served by this event:

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

The event will be hybrid, including face-to-face events in Dublin and the option to attend online.

2 days with:

·   	1 plenary sessions of the Core group – 2h

·   	1 plenary session for Policy group – 3 h

·   	1 plenary session for WG1 – 2h

·   	1 plenary session for WG2 – 2h

·   	1 plenary session for WG2 – 2h

·   	1 plenary session – meeting with members from the Irish FinTech Sector – 2h

1.3. The plans and objectives of the activity

- The primary objective of this meeting is to inform  and advance Fin-AI’s policy agenda

- The core group members will discuss the on-going status of the Action. They will look at the progress regarding the deliverables and construction of GP3 report.

- WGs meetings will take place to review the achievements of the group, working on the WG’s reports and strategy for GP4.

- The conference will present the working research of the members of most of the WGs with a view to enhancing cooperation and exchange of ideas.

1.4. How the activity serve towards the achievement of the MoU objectives;

Obj 2 - Research Coordination 2

The development of conceptual and methodological tools for establishing when black-box models are admissible and, to the extent possible, making them more transparent and/or replacing them with interpretable and explainable models.

Obj 3 - Research Coordination 3

To receive input from regulators and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence applications.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

The meetup calendar event will be set up closer to the time of the event and the event will be communicated to members through the Action newsletter.

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from the Fintech Industry and from academia and policy makers from across at least five COST countries.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

A policy paper around AI and data protection policy, which will satisfy the 7th deliverable of the Action (allocated to WG1 and WG2) for providing position papers, aimed at regulators and policy-makers, on methodology (with examples of formal criteria) for testing AI techniques in real-time

A dedicated website will make the presentations and results available.

Substantial transfer of knowledge from experienced researchers to PhD students (and vice versa) who will have travelled from numerous COST countries (at least 5 countries).

We expect a long-lasting effect on social interactions from this kind of event.

Improved understanding of academic state-of-the art in AI for Finance, training slides, presentation slides and new research challenges for ML in Finance developed by participants available on the Action website.

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the Machine Learning, AI and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

Greater awareness of the role of data protection and privacy in the financial industry and in financial technological development

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

Application and spread of knowledge developed during the meeting across industries, academia and policy

Enhancement of the Fintech sector by presenting new research aproposals and results.

Facilitation of the GP3 reports writing.

3. Title of meeting

Machine Learning, Artificial Intelligence and Data Protection in Fintech Conference

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

July 6th

6. End date and time

July 8th 2022

7. City

Dublin

8. Country

Ireland

9. Total number of expected participants

50

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

50

# 11 to add Vasile Alecsandru STRAT  + WGs + Core

Contact email: codruta.mare@econ.ubbcluj.ro , codruta.mare@ubbcluj.ro, vasile.strat@bbs.ase.ro, danpele@ase.ro

1.Description

This event is scheduled at about the middle of GP3. Thus, it provides the opportunity for the Core Group members to have an overview of the activities carried out till then in GP3, along with planning the remaining of GP3. Additionally, WGs members will be able to discuss the strategy of each WG, and present their works in a conference session of the most famous Scientific event of the Bucharest University of Economic Studies, ICESS 2023. Among the invited speakers at this event will be Tudor Doman (Romanian Financial Supervisory Authority) and Raluca Micu (National Bank of Romania, Head of the Payments Oversight Division). This event will also provide the possibility for the Networking Tools Committee to meet and set the strategy for the second half of GP3.

Core group meeting

WG Meetings

Deliverables:

Strategy to engage stakeholders in the Action. Deliverables of WGs.

Objectives tackled: 3, 5, 7, 8, 9, 10, 11, 15, 16

1.1. How the networking activity serves the MoU objectives;

As this event is scheduled in the middle of GP3, it will provide an opportunity for the participants to make an overview of the activities and achievements and plan for the remaining period.

The event will host the Core group meeting, along with WGs meetings.

Representatives of the Romanian Fintech Association will be invited to enhance the cooperation with the stakeholders. Also guests from the supervisors

Participation will be in person and will be connected with ICESS 2023, the most important Scientific event of the Bucharest University of Economic Studies.

It therefore contributes to the following MoU objectives:

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

2 days with:

·   	1 plenary sessions of the Core group – 2h

·   	1 plenary session for WG1 – 2h

·   	1 plenary session for WG2 – 2h

·   	1 plenary session for WG3 – 2h

·   	1 plenary session – meeting with the Romanian FinTech Sector – 2h

.          Participation to sessions of ICESS 2022

1.3. The plans and objectives of the activity

The main goal of the 2-day event is to facilitate the meeting of:

1.      The core group members to discuss the status of the Action, the status of the deliverables and construction of GP3 report.

2.      WGs meetings to evaluate the achievements of the group, build the WG’s reports and strategy for GP4, presentation of the research conducted by the group members in order to enhance cooperation.

3.      Meeting the Romanian FinTech representatives and the local IT companies working in the field in order to enhance the cooperation with the stakeholders.

4. Attend the sessions of ICESS 2022 in order to increase the visibility of the network and attract new members for GP4

1.4. How the activity serves towards the achievement of the MoU objectives;

It shorts stakeholder involvement. It supports the Fintech Report of the Balkans.

1.5. Link to website (mandatory: on meetup: ICESS 2023, Thu, Jun 8, 2023, 9:00 AM | Meetup )

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from industry and policy makers.

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

Abstracts of presentations will be made available online (upon permission by authors)

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

The event will also allow interaction among its members.

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

Implication in the Fintech sector with research proposals.

Facilitation of the development of the network.

3. Title of meeting

TBD

4. Face to face, hybrid, virtual?

Face to Face

5. Start date and time

09 00 8th of June 2023

6. End date and time

17 00 9th of June 2023

7. City

Bucharest

8. Country

Romania

9. Total number of expected participants

40

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

30

# 10 WG 3 meeting in Winterthur (3nd Grant period) -

“Transparency of Digital Asset Investments”

(proposers: Peter Schwendner / Marcus Wunsch)

Contact: scwp@zhaw.ch, wuns@zhaw.ch

1.Description

Working Group 3 of the COST Action CA 19130 Fintech and Artificial Intelligence in Finance will organise an interdisciplinary meeting open to all working groups of the Action.

In line with the item “Capacity Building 2”, we intend to bring together experts from technological, quantitative, and economic fields in order to discuss research questions relating to digital assets and investing that can best be addressed in an interdisciplinary setting. Moreover, there will be ample time for open discussions regarding past accomplishments and current deliverables of the Action,  as well as future joint research projects. In particular, we will address Deliverables 4 and 10 of the Action.

1.1. How the networking activity serves the MoU objectives;

The meeting will serve RCO 2-4 as well as RCO 6 of the MoU objectives.

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Format: 		face-to-face (NOT hybrid)

Rough schedule: 	9am - 3pm: 		plenary sessions

3h45pm - 4h45pm 	Action MC meeting

5pm - …:		Apéro, dinner

1.3. The plans and objectives of the activity

The meeting will consist of several plenary sessions of invited speakers and ensuing discussions. A main goal is to exchange and discuss research ideas in order to progress on the Action deliverables as well as forming new research project partnerships.

1.4. How the activity serve towards the achievement of the MoU objectives;

Through face-to-face meetings and formal as well as informal discussions, there will be a forum for disseminating current research results and cross-fertilising research ideas among participants. The audience will be a mix of academics and practitioners to discuss the validation and plausibility of approaches toward making digital asset investments more transparent.

1.5. Link to website

https://www.meetup.com/de-DE/fintech_ai_in_finance/events/288642734/?isFirstPublish=true

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

Natalie Packham: expert in blockchain and cryptocurrencies, as well as quantitative finance

Simon Trimborn: expert on network models applied to cryptocurrency exchanges

Artur Sepp: seasoned investment expert and quant working in the crypto space

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

The working group meeting will facilitate the establishment of joint research projects with publications as outputs.

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

The face-to-face working group meeting will strengthen the cooperation among researchers and across working groups.

2.3.  Technology: e.g. a prototype, a database; NA

2.4. Societal applications

3. Title of meeting  		“Transparency of Digital Asset Investments”

4. Face to face, hybrid, virtual? 	face-to-face

5. Start date and time 		26 May 2023 9am

6. End date and time  		26 May 2023 evening

7. City 				Winterthur

8. Country			Switzerland

9. Total number of expected participants 			30

10. Requested Local organizer support 				CHF 2’000,-

11. Number of participants to be reimbursed for travel 		10

# Samples

## Training school sample

Grant period goals it will address

To collect and assess potential approaches for improving the identified robustness issues of problem-of-other-people-fields (PoPF); To increase the contributions of Young Researchers and Innovators from ITC countries by 20% compared to last year, while safeguarding gender balance and enhancing diversity in the Action;

Description

This Training School will highlight to young researchers but also to others interested in the topic, the challenges of the robustness of PoPFs and will discuss the latest findings on how to improve it. The trainers will be mainly selected from the Action, i.e. WG1. Additional expertise will be invited to discuss different cultural norms affecting PoPF robustness. Using the MoU of this Action as a hands-on example trainees will learn to assess PoPF robustness and will be invited to find their own solutions on how to further increase it. Financial support will be provided to PhD students, with priority to improve gender balance and for students from ITC countries. Established researchers with own travel funds can join the Training School without reimbursement by the Action. As hotels are still cheap at that time of the year the daily allowance will be reduced.

Outputs

Improved understanding of PoPF robustness, training slides and new solutions for PoPF robustness developed by participants available on the Action website.

## Working group sample

Grant period goals it will address

To finalise the review of large-scale geo-engineering technologies, while increasing the number of participants to WG2; To start discussions on the objectives of the Hitchhiker’s Technologies Society; To increase the contributions of Young Researchers and Innovators from ITC countries by 20% compared to last year, while safeguarding gender balance and enhancing diversity in the Action;

BigBuild (www.bigbuild.conf) is the largest conference of the geoengineering industry in East Europe.

Description

The Workshop (one morning, two afternoon sessions) shall highlight the WG2 findings to the community and attract new members to WG2. In addition, participants will be asked about their expectations on a future HGT society. Reimbursement will be provided to WG2 members presenting at the Workshop, following the Action’s criteria for reimbursement entitlement. The Annotated Rules for COST Actions do not allow the conference organisers to charge registration fees from the COST Action participants invited to the Workshop. LOS will be used instead to cover conference expenses (e.g. room rentals).

Output:

Dissemination of WG2 results in a community important for HG Technologies, promotion for WG2, input for the HGT society

## MC and core group and WG meetings sample

Grant period goals it will address

To collect and assess potential approaches for improving the identified robustness issues of problem-of-other-people-fields (PoPF); To finalise the review of large-scale geo-engineering technologies, while increasing the number of participants to WG2; Analyse the results of the survey among intelligent doors and discuss it with end-user organisations; To start discussions on the objectives of the Hitchhiker’s Technologies Society; To increase the contributions of Young Researchers and Innovators from ITC countries by 20% compared to last year, while safeguarding gender balance and enhancing diversity in the Action;

Description

During the Core Group meeting (approx. 0.5 days) the report to the MC about the Action status will be prepared as well as the creation of the HGT society will be discussed first time. Special focus will be given to catching up on GAPG 2. The WGs will meet in parallel (approx. 2 days) to discuss their tasks and upcoming outputs and then report to the plenary (2h). WG1 will focus mainly on weak robustness of PoP fields against Manager’s attention. WG2 will agree on the review and discuss how to attract participation. WG3 will start the in-depth analysis based on the results of the last year’s survey.  WG4 will discuss communalities among the target technologies and brainstorm on their societal impacts. A renowned researcher from Betelgeuse will be invited to give a virtual keynote during the panel on the development of Hitchhiker’s technologies in their solar system. The MC (approx. 0.5 days) will discuss the HT society objectives in addition to the Action’s progress

Output:

Draft objectives for HGT society, draft collection for robustness approaches to problem of-other-people-fields, plans for the outreach of WG2, final review of large-scale geo-engineering technologies, focus points for the in-depth analysis of intelligent doors’ psychological problems (WG3).

## Working group sample

Grant period goals it will address

Analyse the results of the survey among intelligent doors and discuss it with end-user organisations; To increase the contributions of Young Researchers and Innovators from ITC countries by 20% compared to last year, while safeguarding gender balance and enhancing diversity in the Action;

Description

This one full-day meeting by WG3 aims to start a trialogue between the Action,  intelligent doors patient organisations and door manufacturers. Results of the WG3 door survey will be presented and the views of patient organisations and door manufacturers will be discussed. Financial support will be granted to WG3 members deeply involved in the analysis of the survey as well as to representatives of the patient organisations, as the latter mostly cannot afford travel expenses. As the meeting will take place in an easy-to-reach location next to the airport, the daily allowance will be reduced.

Output:

Presentations, report of the meeting, improved contacts to patient organisations and manufacturers

## Mobility STSM, et al

To increase the contributions of Young Researchers and Innovators from ITC countries by 20% compared to last year, while safeguarding gender balance and enhancing diversity in the Action; To increase the understanding of social factors impacting the uptake of Hitchhiker’s Technologies (HT) by comparing the social response to HT for at least 15 different COST countries.

Like last year the grants for the mobility of Researchers and Innovators will be awarded via three calls. To reinforce their work, per call 50% of those grants will be ringfenced for WG4, i.e. for grants investigating social barriers impeding the uptake of Hitchhiker’s Technologies.

Mobility of Researchers and Innovators

| Grant Period Goal(s) it will address: |  |
| --- | --- |
| Description | STSMs will be strictly allocated only if the outcome is completion of a deliverable or objective that is not yet finished or achieved. That is in particular deliverable 3 and 5 and additional ones, as decided by the Grant Award Coordinator in cooperation with the Action Chair. Preference will be given to junior researchers and ITC countries. Proof of travel costs has to be provided. Daily allowance is limited to 160 EUR/ day with potential adjustments in line with the EU country coefficients as applied in the HE programme. Deadlines will be every month on the 15th, response until the end of the month, mission from the next month onwards. |

# 7 Maria Iannario Training School Naples (proposer)

Contact email: maria.iannario@unina.it

Check list

1.  	Special issues

A special issue on FRONTIERS IN APPLIED MATHEMATICS AND STATISTICS (or Mathematics) on the topic "Advanced Statistical Modelling for Fintech, financial inclusion and inequality” (Analysis and Applications of Statistics and Data Science) should be launched during the Training School (TBC).

2.  	Deliverables/Objectives completed

A discussion paper for possible approaches to building a statistically valid back-testing framework is one of the deliverables (see point 5 GP3 - Overall deliverables).

Methodological discussion papers on AI models to generate “failed trials” of investment product producers and on quantitative strategies with the usage of the promising field of network data analysis exchanges and regional consolidation platforms optimised for accessibility to all partners represent another AFFINE deliverable (see point 10 GP3 - Overall deliverables).

Key software (codes, packages) in line with WG objectives will be developed (see point 12 GP3 - Overall deliverables).

Last day is also dedicated to receive input from regulators (Bank of Italy) and practitioners' communities and to validate results with regard to increasing transparency of Artificial intelligence and Fintech applications (obj 3; 15 - overall objectives).

The training school imply also the dissemination of the results of the Action's activities to the scientific community, European institutions and to the general public → making posters and abstracts of of speed talk presentation (introduction day) available on the COST Fin-AI website.

3.     High-quality event, also potentially for continuation (show evidence that it previously was a successful event)

We experienced the previous meeting organized in the frame of Cost Acrion in Naples with 70 in person participant and more than 100 persons on line (‘https://fin-ai.eu/diversity-workshop-naples2022/). The event was attended by academics and stakeholders and reported in several national and international newspapers.

We also recently organized the second edition of the Summer School in Social Statistics (https://www.labstat.it/socstat22/) with more than 100 participants.

Furthermore, on a close topic we are dealing with the Advanced Training Course in Expert of the sector credit and insurance expert within the same Department.

4.    Joint events with working group meetings.

We have core group meeting, diversity meeting and policy meeting scheduled during the three days.

5.   Check if we have separate working group meetings and have at least two

working groups together

6.   Policy makers should be involved, i.e. wider outreach to others.

One keynote is a policy maker (coming from Bank of Italy, september 15). Technicians and stakeholders will be welcome. IBM researchers have already expressed their interest in taking part in the in training school.

1.Description

The Training School in Advanced Statistical Modelling for Fintech, financial inclusion and inequality is offered by University of Naples Federico II and is hosted by the Laboratory for Statistical Data Analysis within the Department of Political Science, University of Naples Federico II in September 2023 (13, 14, 15).

The School is designed for COST members, stakeholders, researchers, PhD students, and possibly brilliant MSc graduates / final-year students interested in Statistics, Probability, Computer Science, Applied Mathematics, and related areas.The trainers have been selected from the Action, across all working groups. Among participants the school will aim at a 50% gender representation and include members from at least 5 different countries, including  ITC members. Preliminary availability by Albania, Bulgaria, France, Greece, Italy, Ireland, Romania, Turkey, Macedonia.

The aim of the Training School (TS) AFFINE is to establish a track of high level courses on advanced and cutting-edge topics in Statistics and Probability with application in FinTech and Artificial Intelligence area. Expertise and regulators will be invited to discuss the future of Finance, related to Digital Finance. Using the Action MoU as practical examples, participants will learn to understand both the challenges and solutions in this field, learn about numeracy related to the latest AI techniques, as well as the latest applications.

The School offers lectures delivered by internationally leading scholars, selected from the Action, across all working groups, on the specific designated topic, and supervised tutorials. During the school participants analyse the results of a survey on ‘Knowledge and use of Fintech products’ administered as part of the CA19130 Action from September to December 2022 and discuss them also with end-user organisations. One of the objectives is to analyse data and assess the presence of diversity and inclusion in the fintech area through appropriate statistical models.

Financial support will be provided to PhD and MSc graduates / final-year students, with priority to improve gender balance and for students from ITC countries. Established researchers with their own travel funds can join the Training School without reimbursement by the Action.

Outputs

To introduce participants to statistical models for analysing complex data structures from large-scale surveys consisting of multiple-choice items.

Present parametric and non-parametric frameworks, joint methods for dimension reduction and clustering, statistical learning for fintech data science, data integration, data pre-processing and data fusion enhancing participants' understanding.

A discussion paper for possible approaches to building a statistically valid back-testing framework is one of the deliverables (see point 5 GP3 - Overall deliverables).

Methodological discussion papers on AI models to generate “failed trials” of investment product producers and on quantitative strategies with the usage of the promising field of network data analysis exchanges and regional consolidation platforms optimised for accessibility to all partners represent another AFFINE deliverable (see point 10 GP3 - Overall deliverables).

Course slides and new solutions from open-source software packages, also developed by participants, will be available on the Action website. Key software (codes, packages) in line with WG objectives will be developed (see point 12 GP3 - Overall deliverables).

Attendance and final certificate

Full attendance of the activities of the TS is mandatory for the participants.

Subject to a positive participation to the program, an attendance certificate will be awarded by University of Naples Federico II and Cost action FinAI (CA19130 – Fintech and Artificial Intelligence in Finance – Towards a transparent financial industry).

1.1. How the networking activity serves the MoU objectives;

The Training School will bridge the gap between academia, industry, the public and governmental organisations by working in an interdisciplinary way across Europe and focusing on innovation.

This event will in particular support all capacity building objectives, with a particular focus on young researchers and PhD students. We will bring researchers together (Obj. 8), transfer knowledge (Obj. 10), organise feedback for PhDs from discussants and audience (Obj 14).

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Preliminaries - virtual

Participants may first acquire the main preliminary information and familiarise with the R environment thanks to the free course offered by the University of Naples Federico II (MOOC- www.federica.eu) Machine Learning e Data Mining in R at

https://www.coursera.org/learn/machine-learning-data-mining-con-r

Face-to-face; 3 days

Wednesday, September 13, 2023

Welcome event

-        14.00. Poster session: participants of the Cost Action CA19130 may present their research. Data analysis collected by VMGs surveys will be the starting point for the discussion on the applied component.

A welcome coffee will be offered during the poster session.

-        14.30. Welcoming speech – Francesco Palumbo, Pro Rector for Teaching

Vittorio Amato, Dean of the Department

Jörg Robert Osterrieder, Cost Action CA19130

-        14.45. Introduction of the course (Maria Iannario)

-        15.00. Methods for dimension reduction and clustering in Fintech surveys

Guest lecture - Angelos Markos, Associate Professor of Data Analysis in the Social Sciences, Democritus University of Thrace - amarkos.gr

Main topic: Clustering mixed type nominal/ordinal/interval data, Joint dimension reduction and clustering

17.00 Gender differences in the knowledge and use of Fintech products: narrative of a survey

Lecture, Claudia Tarantola, University of Pavia,

https://sites.google.com/a/unipv.it/claudia-tarantola/home

-        17.30. Laboratory lectures – supervised tutorials as well as individual and team work

Lab  :   http://www.amarkos.gr/clustrd/

http://www.amarkos.gr/clustrd-part2/

Thursday, September 14, 2023

-        9.30. Latent variable models for Financial knowledge (3 hours)

Guest lecture – (TBC)

Main topic: Latent variables, Classical Test Theory, Item Response Theory, IRT models for polytomous items, Hierarchically Structured Modelling: Tree-Based Models, multivariate and categorical statistics, Multidimensional IRT, model selection.

13.00. Lunch

-        14.00. Laboratory lectures – supervised tutorials as well as individual and team work

Lab  : Item Response Theory and financial knowledge in R

-        18.00 Social event

Friday, September 15, 2023

### -        9.30. Hybrid approach for the analysis of complex data structures

Guest Lecture – Alfonso Iodice D’Enza, Associate Professor in Statistics, University of Naples Federico II - https://www.docenti.unina.it/iodicede

Main topic: Hybrid methods; Dimension reduction and clustering methods; Implementations of dimension reduction for continuous, polytomous and mixed data, complex categorical structures

Short lectures

11.30 Complex data structures in Finance

Lecture Petre Lameski, Professor at University of Sts. Cyril and Methodius in Skopje, Macedonia Faculty of Computer Science, https://github.com/lameski

12.00. Panel data for assessing FinTech, financial inclusion and income per capita

Lecture Codruta Mare, Associate Professor of econometrics, https://econ.ubbcluj.ro/cv.php?id=283

-        12.30 Financial inclusion: assessing the role of digital payments during the pandemic using single item latent trait response models

Lecture - Researchers by Bank of Italy, Retail Payment Instruments and Services Directorate,

The latter contributes to the following objectives of the Action:

Improve the knowledge about financial inclusion among research institutions and infrastructures, businesses and other socio-economic actors

-        13.30. Lunch

-        14.30. Laboratory lectures 2 hours – supervised tutorials as well as individual and  team work- evening

Lab  : https://github.com/alfonsoIodiceDE/hybrid_analysis_complex_categorical

-        16.30. Summary, feedback, alternative methods, wrap-up (Maria Iannario)

1.3. The plans and objectives of the activity

Training school for researchers, PhDs and Master students. We will invite trainers and participants. 3 workshops delivered by internationally leading scholars (3h each) on a dedicated topic with implementations in our COST Action area will be given. Two Lab sessions (3h each) show how to repeat the results presented in the theoretical sessions through the use of open source software. One afternoon is dedicated to special training on transferable skills. One afternoon for social networking. A welcome event with a poster session where participants may show their research activity will also be provided. The event allows an exchange of information on activities even by those who are not currently part of the action. Last day is also dedicated to receive input from regulators (Bank of Italy) and practitioners' communities and to validate results with regard to increasing transparency of artificial intelligence and Fintech applications (obj 3; 15 - overall objectives).

1.4. How the activity serve towards the achievement of the MoU objectives;

The event brings together members of the Cost action, academia, industry, the public and governmental organisations and also contributes to the following MoU objectives: by including participants from different areas and disciplines, and possibly new members currently outside the CA19130 network.

Geographical, age and gender balance will be taken into account when accepting participants.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/fintech_ai_in_finance/events/289839290/

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

Guest lecture - Angelos Markos, Associate Professor of Data Analysis in the Social Sciences, Democritus University of Thrace - amarkos.gr

Research Interests

Clustering mixed type nominal/ordinal/interval data Joint dimension reduction and clustering

Guest lecture – Full professor, expert in Latent Variable Models and complex data (TBC)

Lecture – Alfonso Iodice d’Enza, Associate Professor in Statistics, University of Naples Federico II - https://www.docenti.unina.it/iodicede

Research interests

Dimension reduction and clustering methods. In particular, his research activity aims to develop incremental implementations of dimension reduction for continuous, polytomous and mixed data, hybrid methods

2. Output

A dedicated website will make the presentations and results available.

Substantial transfer of knowledge from experienced researchers to PhD/master students (and vice versa). We expect a long-lasting effect on social interactions from this kind of event.

Improved understanding of academic state-of-the art in AI for Finance, training slides, presentation slides and new research challenges for ML in Finance developed by participants available on the Action website.

Materials (slides, data, codes) about TS AFFINE will be updated on the Action website.

3. Title of meeting

Advanced Statistical Modelling for Fintech, financial inclusion and inequality (AFFINE)

4. Face to face, hybrid, virtual?

Face to face

5. Start date and time

Wednesday 13 – time 14.30

6. End date and time

Friday 15 – time 17.00

7. City

Naples

8. Country

Italy

9. Total number of expected participants

25

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

20

For summer schools, in addition:

12. Number of trainers

5

13. Number of trainees

20

# 13 Training School Tirana

Contact email: elda.xhumari@fshn.edu.al; suela.maxhelaku@fshn.edu.al; joerg.osterrieder@bfh.ch; endri.xhina@fshn.edu.al; wuns@zhaw.ch; codruta.mare@gmail.com; valerio.poti@ucd.ie;

1.     Description

The challenges of Fintech and Artificial Intelligence in Finance will be highlighted for young researchers as well as others interested in the subject during this Training School. It will also cover the most recent research on how to improve it, with a particular focus on extending it towards Smart Financial services. The future of finance and digital finance will be discussed with other experts. Students will learn about the problems and potential solutions in this subject, as well as the most modern AI approaches, their shortcomings, and new applications, using the MoU of this Action as a practical example.

The main deliverables that this training school will focus on are as follows:

·         Report on good examples and best practices for a transparent finance industry with guidelines to improve transparency;

·         10. A position paper and roadmap on mitigating risks connected with the increased use of digital assets;

The main objectives that this training school will focus on are as follow:

·         7. Create an excellent network of researchers in Europe with lasting collaboration beyond the lifetime of the Action.

·         8. Bringing technological, quantitative and economic researchers together, to tackle future research that can only be done in an interdisciplinary setting, and getting actively involved in the blockchain and FinTech communities across Europe, to constantly monitor developments, get input and disseminate results.

·         10. Transfer knowledge in terms of expertise, scientific tools and human resources across the different disciplines and between academia and industry.

·         11. Establish an inclusive community of researchers on methodological and technological themes in Machine Learning and Artificial Intelligence, to promote Early Career Investigators and increase their visibility.

·         12. Overcome the siloing of research topics by country and achieve geographical and demographical diversity, with special attention to COST Inclusiveness Target countries.

·         13. Prepare competitive European researchers for a fruitful career in an international environment through intensive use of Short Term Scientific Missions (STSM) and joint educational programs with industrial partners.

·         15. Disseminate the results of the Action's activities to the scientific community, European institutions and to the general public.

Co-organizers of the training school:

1.  Osterrieder Jörg Robert - joerg.osterrieder@utwente.nl

2. Wunsch Marcus - wuns@zhaw.ch - Risk management in Decentralized Finance (deliverable no.10)

3.  Codruta Mare - codruta.mare@gmail.com

4. Valerio Poti - valerio.poti@ucd.ie - Seminar on applications of NLP for financial econometrics or more broadly on trends in FinTech

5. Elda Xhumari, Suela Maxhelaku, Endri Xhina - Elda.xhumari@fshn.edu.al; suela.maxhelaku@fshn.edu.al - Using machine learning to improve risk management (deliverable no. 4); Endri.xhina@fshn.edu.al; suela.maxhelaku@fshn.edu.al; elda.xhumari@fshn.edu.al; -   Modeling a Business Process as an Intelligent Agent (deliverable no.4)

Also is planned to deliver a paper for the deliverable no. 8. Report on good examples and best practices for a transparent finance industry with guidelines to improve transparency.

1.1. How the networking activity serves the MoU objectives;

Students, young researchers, and anybody else interested in the current FinTech issue are the target audience for this training school. The key problems and solutions in the field of fintech, technologies used and challenges, will be discussed with the attendees.

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid; 3 days

Wednesday: Invited guest lectures

Thursday morning:  Mini-workshop, Social Event

Friday morning: Summary, feedback, wrap-up

Detailed schedule

Wednesday, 26 April 2023

09.00 – 09.30 – Registration and Coffee Break

09.30 – 10.00 – Welcoming speech, University of Tirana Rector and Dean (remote participation possible via Zoom)

10.00 – 12.00 – Opening session, part 1: collect background, define priorities and tasks (remote participation possible via Zoom)

12.00-13.00 – Lunch break

13.00-14.30 – Session 2: Presentations focusing on the technologies used for the application of artificial intelligence in the economy (remote participation possible via Zoom)

14.30-15.00 – Coffee break

15.30-17.00 - Session 3: Closing remarks, discussion first day (remote participation possible via Zoom)

17.00 – Social activity

Thursday, 27 April 2023

09.00 – 09.30 – Registration and Coffee Break

9.30 – 12.00 – Session 4: Preparation and configuration of tools

12.00-13.00 – Lunch break

13.00-14.30 – Session 5: Overview, tool demos

14.30-15.00 – Coffee break

15.30-17.00 Session 3: Closing remarks, discussion

17.00 – Social activity

Friday, 28 April 2023

09.00 – 09.30 – Registration and Coffee Break

9.30 – 12.00 – Wrapping up

11.00 – 12.00 – Coffee break

12.00-14.00 – Reporting (remote participation possible via Zoom) and closing

1.3. The plans and objectives of the activity

Invited trainers will provide mini-workshops on a specific subject associated with the COST Action thematic. Also, students and researchers will discuss about the challenges. We will organize a training session on portable skills and career possibilities in order to create a network between academy and industry. Furthermore, social networking is planned for one afternoon.

1.4. How the activity serves towards the achievement of the MoU objectives

Organizing a session specifically for researchers to gain feedback from the discussants and the audience, the event brings together members of the cost action, industry and academy; and also contributes to the MoU's following objectives. Participants from other fields and disciplines are invited to participate considering age and gender balance.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

Not created yet

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be contacted, but we hope to have distinguished speakers from CA19130 and from Faculty of Natural Sciences, Department of Informatics, and a representative from each co-organizer of Cost Member Institution industry and policy makers.

2. 	Output

- The presentations and results will be made available on a web portal.

- Significant information transfer from participants.

- Long lasting impact on social relations.

- Enhanced knowledge for the latest technologies and upcoming challenges.

- Increasing the interest of scientific researchers in the field of Fintech and AI in Finance

3. 	Title of meeting

COST FinAI - Fintech and AI in Finance - Training School for the latest technologies and upcoming challenges

4. 	Face to face, hybrid, virtual?

Hybrid

5. 	Start date and time

April 26, 9am

6. 	End date and time

April 28, 2pm

7. 	City

Tirana

8. 	Country

Albania

9. 	Total number of expected participants

60

10.  Requested Local organizer support

6000

11.  Number of participants to be reimbursed for travel

10

12.  Sample materials

A.  	We have a full master program in Artificial Intelligence:

Programming for AI and Data Science

Introduction to Artificial Intelligence

Data Engineering

Microservice architectures

Semantic Web Technologies

Business Intelligence

Big Data and Cloud Computing

Information Retrieval and Natural Language Processing

Human Computer Interaction and Data Visualization

Process Mining

Deep Learning

Data Mining

B.      Research works

C.      Research works in process:

-         Modeling a Business Process as an Intelligent Agent

-         Using machine learning to improve risk management

D.      Lectures Notes prepared in the framework of the Digital Transformation through Artificial Intelligence (AI), Blockchain, Cybersecurity and Data Protection in the context of EU Integration Jean Monnet Module (Endrit Xhina COO, Suela Maxhelaku and Elda Xhumari Module Leader)

# 8 Alla Petukhina Training School Berlin

Contact email: alla.petukhina@htw-berlin.de, erlwein@htw-berlin.de

1.Description

The Training  School in Berlin is targeted at students and young researchers and all interested in the contemporary topic of sustainable finance, more specifically (Measuring climate risk for financial applications). The instructors will be mainly selected from the Action and across all working groups. The participants of this School will learn the main challenges and solutions in the field of sustainable finance: incorporation of climate risks to stress-testing, risk scores, climate value-at-risk.

Plan: we will invite Students from Ukraine (list of Unis).

Financial support will be provided to youth, with priority to improve gender balance and for applicants from ITC countries. Established researchers will be expected to use their own travel funds, especially from non-ITC countries.

1.1. How the networking activity serves the MoU objectives;

Overall, this school will support all capacity building objectives, with a particular focus on youth interested in FinTech, students and potential PhD students:

We will bring researchers together (Obj. 8), transfer knowledge (Obj. 10), organise feedback for the participants from discussants and audience (Obj 14).

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

Hybrid; 5 days, each day 3 hours in the morning and 3 hours in the afternoon

Monday morning - Arrival and welcome;

Monday afternoon Tuesday morning - lectures from invited speakers (academy and industry);

Tuesday Afternoon - Introduction to the Project (Dataset, tasks)

Wednesday, Thursday Morning  - Work in groups on projects

Thursday afternoon - Social event (Preliminary: tour to the industry)

Friday morning: Presentations and discussion of Projects’ results, evaluation..

Wednesday afternoon: Social event

Tuesday morning, Thursday morning:  Mini-workshop

Friday afternoon: feedback, wrap-up

Preliminary lectures topics: Introduction to data-based  mathematical modelling, introduction to data science, introduction to  topics in sustainable finance, Programming in R & Python (with focus on stat finance), industry talks from financial institutions on motivation of climate risk modelling for investment projects.

1.3. The plans and objectives of the activity

To do

1.4. How the activity serve towards the achievement of the MoU objectives;

- The event brings together member of the cost action and also contributes to the following MoU objectives: by including participants from different areas and disciplines, and involve possibly new members currently outside the CA19130 network

- by organising a session dedicated to ECI and PhD students to receive feedback by discussants and the audience

- Geographical, age and gender balance will be taken into account when accepting PhD students.

- Two banks will be involved into the work of the school: DKB and DB risklab, what will increase the link with industry participants (what FinAI currently is missing)

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

https://www.meetup.com/fintech_ai_in_finance/events/288723960

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

To be confirmed. They are the distinguished speakers from CA19130, from other academic institutions and policy makers.

Additionally we plan to invite practitioners, who work on this topic at two Banks located in Berlin (DKB and Deutsche Bank  Risklab).

2. Output

Results  will be presented on a dedicated website.

Knowledge transfer from experienced researchers to students (and vice versa).

long-lasting effect on social interactions due to planned activities.

Improved understanding of FinTech issues

Newsletter of FinAI

Webpage on WG1 fin-ai.

Deliverable contribution missing

3. Title of meeting

COST FinAI Training school "Data science for sustainable economics and  finance "

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

February 20, 9am (TBC)

6. End date and time

February 24, 5pm (TBC)

7. City

Berlin

8. Country

Germany

9. Total number of expected participants

30

10. Requested Local organizer support

5000

11. Number of participants to be reimbursed for travel

10

# ITC conference and  Dissemination grants

# Please describe here, how the Presentation at Conferences organised by Third Parties shall be implemented by the Action (for example the scientific priorities of the addressed Working Group(s), how the COST Principles will be addressed, what conferences will be targeted (if feasible with link to the conference(s)), type and number of calls for applications etc.)

# Dorina Kripa Training School Durres

Contact email: dorinakripa@gmail.com, gisjana.tahiri@gmail.com, lleshlleshaj@feut.edu.al, numani_eni@yahoo.com

1.Description

Today we live in a dynamic world, where technology is the key word in everyday life but also in professions that have advanced over time. The world of finance is a field that has advanced a lot and is changing every day. Government policies, projects, businesses and even their products have changed by always being close to technology and using it as an optimization tool. For this reason, it remains the duty of educational institutes to prepare professionals for a changing world. Young researchers have a very dynamic world to explore and enrich with studies.

For this reason, as a way to create the opportunity for students (not only of the economics faculty) but also for current professionals to get new knowledge about FinTech but why not also update them, we thought of organizing a summer training. The days chosen to take place create the possibility of participation even for people who may currently be engaged in work. Using the long experience in the field of Finance but also the good knowledge of the development of the labor market today in Albania, we think that it is more valuable to develop basic knowledge modules related to fintech, bringing the latest studies in this field into focus. but also a summary of real products created in recent years (concrete examples as case studies).

1.1. How the networking activity serves the MoU objectives;

As emphasized above, the main goal consists in creating a common language between professionals, businesses, where knowledge and needs serve as a connecting bridge. More and more businesses need the use of technology and as a result they need trained young people. This situation also creates a great opportunity for all young professionals and researchers to carry out pioneering studies in this field. As the market itself has shown us, physical borders no longer exist. For this reason, the purpose of this training is to demonstrate a global language, without limitations but with cooperation between researchers and young professionals.

1.2 The format (face-to-face, hybrid or virtual) and rough schedule;

Hybrid; 3 days

Friday: Module lecturer (different lecturers depending on the module)

Saturday: case study, workshop

Sunday : group discussion about a current situation

1.3. The plans and objectives of the activity

This activity is a good opportunity for all interested parties to meet in order to create a functional network. (i.e. representatives of main technology companies that meet students or other interested parties). One of the main objectives is to arouse interest in this field among young professionals and also the help that can be given to young researchers in specifying their field of study. Phd students from the University of Tirana and not only will be invited to this activity.

1.4. How the activity serve towards the achievement of the MoU objectives

It will be an activity that will bring together young professionals, students in the fields of economics and technology, researchers, but also business representatives. In addition to gaining knowledge and providing an inclusive module in this field, it will also be possible to create a functional network.

1.5. Link to website (mandatory: on meetup: https://www.meetup.com/Fintech_AI_in_Finance/ )

Not created yet

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

We are in talk with experts of the field, but the names have not yet been determined. The names of the experts will be decided in a second moment, after the discussion with them.

2. Output

- Written lectures and the presentation

- Notes for further study arising from the workshop

- DL with people interested in this field

- Formulation of study topics related to this field

3. Title of meeting

COST FinTech - Training for a constantly changing financial world

4. Face to face, hybrid, virtual?

Hybrid

5. Start date and time

June 30, 9am

6. End date and time

July 2, 4pm

7. City

Durres

8. Country

Albania

9. Total number of expected participants

30

10. Requested Local organizer support

4000

11. Number of participants to be reimbursed for travel

10

12. Number of trainers

6

13. Number of trainees

30

14. Materials

- For the moment we have 7 modules on FinTech in our syllabus, 2 in bachelor's level and 5 in master's.

  - Fin Tech and the banking system

  - Fin Tech, legislation and integration in BE

  - Fin Tech and the new challenges in banking regulation

  - Fin Tech and investment opportunities

  - Adoption of investment legislation in a word Fin Tech

  - Risk and financial technology

  - Fintech and its impact on the real estate market

- Also as a department, we have won a Jean Monnet project on FinTech. The team is preparing new modules and several workshops that will be an added value for our trainers and an experience in which we will share our ideas with techno business

- The modules and presentations that will be shared in the summer school, will be prepared by our trainers during this period, so that they are as up to date as possible with a dynamically changing world.

15. Program

- Starter kits: Before the start of the summer school, a package with online material will be sent to all participants.

- During summer school:

  - focused lectures by academics

  - focused keynotes from business representants

  - project work

  - social events

- ·At the end of summer school

  - Business case &pitch competition

# GP 2Vasile Alecsandru STRAT  + WGs + ROMANIAN FINTECH REPORT 2022

Contact email: codruta.mare@econ.ubbcluj.ro, codruta.mare@ubbcluj.ro

1.Description

WG Meetings

Romanian Fintech Report 2022

1.1. How the networking activity serves the MoU objectives;

As this event is scheduled at the end of GP2, it will provide an opportunity for the participants to discuss and plan for the next period and also conclude the current one.

The event will host WGs meetings and the presentation of the Romanian Fintech Report 2022. There will be opportunities to meet industry representatives and representatives of the regulators.

It therefore contributes to the following MoU objectives:

Obj. 8 - Obj. 10 Obj 11 Obj. 14

1 day with:

Fintech Report 2022

WG meetings

The main goal of the 1-day event is to facilitate the meeting of:

1.      WGs members

2.      Meeting the Romanian FinTech representatives, the local IT companies working in the field, and regulators and supervisors  in order to enhance the cooperation with the stakeholders.

https://www.meetup.com/fintech_ai_in_finance/events/288815025/?isFirstPublish=true

ROMANIAN FINTECH REPORT 2022, Fri, Oct 28, 2022, 9:00 AM | Meetup

1.2 The format (face-to-face, hybrid or virtual) and rough schedule (e.g. 2 hrs Action MC meeting, 2 days parallel sessions of WG meetings, 2 hrs plenary session of all WGs);

1.3. The plans and objectives of the activity

1.4. How the activity serves towards the achievement of the MoU objectives;

1.5. Link to website (mandatory: on meetup:

1.6. Possible keynote speakers and trainers and their relevant expertise could be also described.

-

2. Output

2.1. Codified knowledge, e.g. publications; patents, websites

Report will be made available after the event.
Implication in the Fintech sector with research proposals.
Facilitation of the development of the network. 
The event will also allow interaction among its members.

2.2. Tacit knowledge: Non formalised knowledge, resulting from the participation in the COST Action networking activities and the social interaction among its members that can also be re-invested in other contexts;

2.3.  Technology: e.g. a prototype, a database;

2.4. Societal applications

3. Title of meeting

TBD

4. Face to face, hybrid, virtual?

Face to Face

5. Start date and time

09 00 28th of October 2022

6. End date and time

15 00 28th of October 2022

7. City

Bucharest

8. Country

Romania

9. Total number of expected participants

480

10. Requested Local organizer support

10000

11. Number of participants to be reimbursed for travel

12